## Sheet2
Hospitality Pricing - Deployment Plan - Phase 2
RLS - 595672
Activities |  | Assignee | Time | Note | Time
Datapump | Oracle | DBA/Agus
Oracle DB: SCPRD Schema: WSPRICE_REPO
Run the SQL scripts
http://subversion.bcliquor.com/svn/Java/DataPump/database/wholesale_price/sourcedb/DataPump_Wholesale_Price.sql.sql
Solution deployment steps
Wholesale Price Service |  | DBA/Bikram
PostgreSQL
Create database: co_db (see DEV for a reference)
Create schema: wsprice_repo (see DEV for a reference)
Create database user: wsprice_repo_app
Run the SQL scripts:
http://subversion.bcliquor.com/svn/Java/DataPump/database/wholesale_price/ targetdb/Wholesale_Price_TargetDB_scripts.sql.sql
Wildfly
-- Create datasource
-- Deploy WholesalePrice web service
SOA
LDB Item Service | PostgreSQL | DBA/Bikram/Keith
Wildfly
SOA
Customer Portal Service
PostgreSQL
Wildfly
Restart Wildfly Application Server hosting Webservices (if Required) |  | DBA
BI Changes
HPI Application Client
Wildfly
HPI Application
Data-files
Blacklisted SKU - csv file upload
Price List pdf file upload

## Sheet4
ID | Task | Assignee
1 | Oracle DB: SCPROD, Schema: WSPRICE_REPO | DBA
Run the SQL scripts
| http://subversion.bcliquor.com/svn/Java/DataPump/database/wholesale_price/sourcedb/DataPump_Wholesale_Price.sql | Done
2 | Postgress DB: | DBA
Create database: co_db (see DEV for a reference)
Create schema: wsprice_repo (see DEV for a reference)
| Create database user: wsprice_repo_app | Done
Run the SQL scripts:
http://subversion.bcliquor.com/svn/Java/DataPump/database/wholesale_price/targetdb/Wholesale_Price_TargetDB_scripts.sql
3 | Datapump PROD (Initial Load) | DBA
Get the datapump script from:
| http://subversion.bcliquor.com/svn/Java/DataPump/database/wholesale_price/wholesale_price_initial_load.xml | Done
(Need to update url/user/password for sourceds/targetds)
4 | After datapump initial load completion. | DBA
| Remove wholesale_price_initial_load from datapump | Done
5 | Datapump PROD (Incremental) | DBA
Get the datapump script from:
| http://subversion.bcliquor.com/svn/Java/DataPump/database/wholesale_price/wholesale_price_incremental.xml | Done
(Need to update url/user/password accordignly for sourceds/targetds)
6 | Postgress DB: | DBA
Execute the following SQL: schema: customerportal
| alter table customerportal.favourites alter column customer_id type varchar(100); | Done
7 | JBoss Service: Bounce the service | DBA
This is required for customerportalservice, so that the column change above can be effective.
8 | Wildfly | DBA
| Create datasource with JNDI name below | Done
jndi-name="java:/app/datasources/WholesalePriceDS"
jdbc:postgresql://ldq9ppgrsql03:5432/co_db
wsprice_repo_app
9 | Wildfly - Wholesale Price Service | DBA
1. Disable Current Wholesale Price Service
2. Deploy Web Service from below Nexus repository
http://nexus.bcliquor.com/repository/maven-snapshots/com/bcldb/service/wholesale-price-ear/1.0.2-SNAPSHOT/wholesale-price-ear-1.0.2-20200821.202015-3.ear
10 | OSB Deployment Steps | DBA
Deploy WholesalePrice Service to OSB
Please import the following jar on OSB PROD and then execute the customization file -
http://subversion.bcliquor.com/svn/SOA/ESB/tags/RLS-595672 - Hospitality Pricing
XSD_WholeSalePriceService.jar
WholesalePriceService_v1.jar
PROD_WholeSalePriceService_v1_ALSBCustomizationFile.xml
11 | PostgreSQL Database - Create INDEX | DBA
CREATE UNIQUE INDEX idx_srv_wholesale_price
ON wsprice_repo.srv_wholesale_price USING btree
(sku, effective_date, customer_type COLLATE pg_catalog."default")
TABLESPACE co_ts;
12 | Copy attached LDB_BLACKLISTED_SKUS.csv to /opt/u01/interface/wholesalepricelist/LDB_BLACKLISTED_SKUS.csv | DBA
13 | Copy/replace price calendar file (pdf) to: | DBA
/opt/u01/interface/wholesalepricelist/
Hospitality_Pricing_Calendar_2020_2021.pdf
14 | Copy/replace hospitality price list (excel) to: | DBA
/opt/u01/interface/wholesalepricelist/Hospitality Price List (Current Period)-en-us.xlsx
15 a | Stop below $U job
| $U [UXAPP/LDBPRD/X] | Operator
- PM_PRDMSG_S – (wom020/wom014 ¦ Item Update)
15 b | LDB Item Service | DBA
PostgreSQL DB
Execute sql script below in PostgreSQL server to create database view LDBItem.v_item
http://subversion.bcliquor.com/svn/SOA/Services/LDBItemServiceV3/branches/HospitalityProducts/sql/ldbitem_v_item.sql
Wildfly AS
1. undeploy exiting LDB Item service
2. deploy LDB Item service from below nexus repo
http://nexus.bcliquor.com/repository/maven-releases/com/bcldb/service/ldb-item-ear/3.1.3/ldb-item-ear-3.1.3.ear
15 c | OSB LDBItemServiceV3.0 | DBA
1. Deploy following Jars along with config plan on OSB PROD
http://subversion.bcliquor.com/svn/SOA/ESB/tags/RLS-595672_LDBItemServiceV3.0/deploy
1. LDBItemServiceType.jar
2. LDBItemService_V3.0.jar along with LDBItemService_V3.0_CustomizationFile_PROD.xml
15 d | Start $U job
| $U [UXAPP/LDBPRD/X] | Operator
- PM_PRDMSG_S – (wom020/wom014 ¦ Item Update)
16 | Increase cpu from 2 to 4 on ldq9pwfext01/02 and bdcpwfext01/02 | Enterprise
Move LUN /opt/u01 from FCC to SSD for ldq9pwfext01/02 and bdcpwfext01/02
September 1st 6:00 AM
17 | HPI Application | DBA
1. Undeploy existing HPI application on WildFly INT5 : Kdcpwfextctrl01
2. Deploy HPI application v2.0.10 on WildFly PROD : Kdcpwfextctrl01
http://nexus.bcliquor.com/repository/maven-releases/com/bcldb/hpi/hpi-web/2.0.10/hpi-web-2.0.10.war
18 | Wildfly - Wholesale Price Service | DBA
1. Disable Current Wholesale Price Service
2. Deploy Web Service from below Nexus repository
http://nexus.bcliquor.com/repository/maven-releases/com/bcldb/service/wholesale-price-ear/1.0.3/wholesale-price-ear-1.0.3.ear

## Sheet1
S# | BI Pricing Checks | Fix required | HPI
1 | [Product].[CURRENT_IND] = 'Y' |  | ???
2 | [ITEM_CATEGORY_NAME] <> 'General Merchandise' | Yes | ldbitem.product_hierarchy.hierarchy_id not in (1001, 1002) | add check in item view
3 | [ITEM_CATEGORY_NAME] <> 'Merchandise Services' | Yes | 1001- General Merchandise ; 1002 - Merchandise Services | add check in item view
4 | [SKU_NO] <> 432526 | NO | ldbitem.item.sku <> 432526 - > Restriction id 25 | Excluded in item view
5 | [PRODUCT_LONG_NAME] not starts with 'SO ' | Yes | ldbitem.v_item.product_name not like 'SO%' | add check in item view
6 | [PRODUCT_LONG_NAME] not starts with 'CSP' | Yes | ldbitem.v_item.product_name not like 'CSP%' | add check in item view
7 | [CUSTOMER_SPECIFIC_IND] <> 'Y' | NO | v_item.csp_ind <> 'Y' | Check exits in HPI application
8 | [PRODUCT_LISTING_TYPE_CODE] <> 'C' | NO | C - BCLS EXCLUSIVE - > Restriction_id = 1 | Excluded in item view
9 | NOT ([PRODUCT_LISTING_TYPE_CODE]= 'S' AND [PRODUCT_LISTING_SUB_CODE] = 'U') | NO | SU - SPECIALTY FUTURE - > Restriction_id = 10 | Excluded in item view
10 | NOT ([PRODUCT_LISTING_TYPE_CODE]= 'X' AND [PRODUCT_LISTING_SUB_CODE] = 'C') | NO | XCBO - RESTRICTED COMMERCIAL ACCOUNTS BACKORDERED - > Restriction_id = 13 | Excluded in item view
|  | NO | XCPD - RESTRICTED COMMERCIAL ACCOUNTS PRIVATELY DISTRIBUTED - > Restriction_id = 35 | Excluded in item view
|  | NO | XCST - RESTRICTED COMMERCIAL ACCOUNTS STOCKED - > Restriction_id = 14 | Excluded in item view
11 | [CURRENT_LIST_STATUS_CODE] not in ('1', '4') | NO | Search in HPI is for status code 2 and 3. Available status codes are 1,2,3,4 | logic is different but the result is same
12 | [WHOLESALE_DIST_METHOD_CODE] <> 'XDOCK' | YES | ldbitem.item.wholesale_distribution_code <> 'XDOCK' | add check in item view
13 | [RETAIL_DIST_METHOD_CODE] <> 'XDOCK' |  | ldbitem.item.retail _distribution_code <> 'XDOCK' | add check in item view
14 | Exclude the "Black List" of SKUs | NO | Used CSV file in HPI application to exclude