## Sheet3
INT5 environment Refresh
Time | Activities
15:00 | - Turn off $U jobs | Operators/Andy
Place $U jobs on hold
The following jobs should be put on hold by the operator.
$U [UXAPP/LDBPRD/X]
- WPO_MSGFLOW_S – (wom013/wom019 ¦ PO)
- PM_PRDMSG_S – (wom020/wom014 ¦ Item Update)
- WMS_INV_ADJUSTMENT_S
- WMS_PO_RECEIPT_S
- WMS_SHIP_CONFIRM_S
- WMS_ITEM_SHIP_UNIT_DIM_S
- WMS_CANCEL_SALES_ORDER_S
| - Retire SOA component | SOA DBA
To retire SOA component, log onto:
http://soaadm.bcldb.com:25001/em
- EBS partition/ EbsPickOrderPublisher [2.1] - (WOM16 ¦ Pick Order)
15:05 | Stop wms application | Andy/Bikram
15:10 | Refresh INT5 database from Production | SQL DBA
prod_94x_m à int5_94x_m
prod_94x_w à int5_94x_w
15:10 | Copy below folders from production | Andy
-- -- D:\wildfly-8.2.1.Final-jdk-1.8.0\dev_94x\deployments\Tecsys.ear\TecsysWeb.war\script\wms\table
-- -- D:\wildfly-8.2.1.Final-jdk-1.8.0\dev_94x\deployments\Tecsys.ear\lib
-- -- D:\wildfly-8.2.1.Final-jdk-1.8.0\dev_94x\deployments\Tecsys.ear\TecsysWeb.war\WEB-INF\classes\jasper
15:40 | Run post database sql script | Bikram
15:45 | Reset Users and Roles | Bikram
15:55 | Start wms application | Andy/Bikram
16:00 | Enable $U jobs | Operator/Andy