## INT5
Line | Phase | TST | TST Step | Task | Details/Comments | Owner | Deployed By | WMS/DCMove | Status | INT Date | Start | End | Duration | Dependency | Deployment Comments
1 | Pre-Requisites
2 | Pre-Reqs | NA | NA | Communication with external users | Vendors, Customers, etc. | Change Mgmt, Lauren | NA | DCMove | Done | NA | NA | NA | NA
3 | Pre-Reqs | NA | NA | Communication with internal users |  | James, Kenny | NA | WMS | Done | NA | NA | NA | NA
4 | Pre-Reqs | NA | NA | Autosys schedules |  | James, Kenny | NA | WMS | Done | NA | NA | NA | NA
5 | Pre-Reqs | NA | NA | Doug to provide Ti-Hi Update File for INT5 and Prod | Need deadline date for Prod Make sure there are no duplicate SKUs in the list | Jorge, Doug | NA | WMS | Done | NA | NA | NA | NA
6 | Pre-Reqs | NA | NA | Verify that the vendor faicing website cannot enter product dimensions anymore after the CPD change | Mark S. | Raymundo | NA | WMS | Done | NA | NA | NA | NA
7 | Pre-Reqs | NA | NA | Ask business if it's okay to live without being able to update volumetrics for 2 week | Done | Raymundo | NA | WMS | Done | NA | NA | NA | NA
8 | Pre-Reqs | NA | NA | Ask business if it's okay to live without being able to update Ti-Hi (other than via scripts) for 2 week | Done | Raymundo | NA | WMS | Done | NA | NA | NA | NA
9 | Pre-Reqs | NA | NA | User list with Role assignments |  | Chaminda | NA | WMS | Done | NA | NA | NA | NA
10 | Pre-Reqs | NA | NA | Populate the shipping schedules for the next few weeks |  | Emily/Lauren | NA | DCMove | Pending | NA | NA | NA | NA
11 | Pre-Reqs | NA | NA | Run a query on BO products for forward pick locations products | Confirm that all the slotted WMS products are not NSWP type in CPD Prod. Adjust either CPD or WMS Slotting based on findings and business direction. | Daniel/Andrei | NA | WMS | Done | NA | NA | NA | NA
12 | Pre-Reqs | NA | NA | Flip certain products from BO product to non-BO | Based on the forward pick slotting location file provided by Ken Deadline needed | Andrei, Chaminda, Ken, Doni | NA | WMS | NA | NA | NA | NA | NA
13 | Pre-Reqs | ?? | ?? | Firewall rules between OSB and WMS need to be opened | RLS Required to get it fixed in Prod | Tony | Networks | WMS | Done | NA | NA | NA | NA
14 | Pre-Reqs | NA | NA | Provide Business with an extract of the shipping schedules | In order to assemble the DC Move lookup table | Emily | NA | DCMove | Pending |  |  |  | 0:00
15 | Pre-Reqs | NA | NA | Buisness to provide us with the DC Move lookup table info |  | Lauren | NA | DCMove | Pending |  |  |  | 0:00
16 | Pre-Reqs | NA | NA | Translate the business lookup entries (XLS) into a deployable file to populate the lookup (SQL) and check into SVN (RICE ID: OM-CON-04) |  | Rajesh | NA | DCMove | NA | NA | NA | NA | NA
17 | Tuesday Jul 10 - Full WMS Configuration
18 | IAM | 335229 | 2 | Change Tecsys DB passwords to standard password | To enable MD Tools to run as now | Daniel | DBA-SQL | WMS | Done | 2018-07-04 | 9:20 | 9:23 | 0:03
19 | IAM | 335229 | 2 | Create 2 new DB Accounts (same permissions as WMSService account); 'datapump' and 'mitool' and share password with WMS Configuration Deployer | This is to enable MI Tool and datapump to work | Daniel | DBA-SQL | WMS | Done | 2018-07-04 | 9:20 | 9:35 | 0:15
20 | IAM | 335229 | NA | Checked the above |  | Andrei/Daniel | NA | WMS | Done | 2018-07-04 | 9:40 | 9:43 | 0:03
21 | IAM | 335229 | 2 | Revert 'System' WMS password to the default |  | Andrei/Daniel | NA | WMS | Done | 2018-07-04 | 9:40 | 9:43 | 0:03
22 | IAM | 335229 | 4 | All WMS SQL Deployments |  | Daniel/Andrei | DBA-SQL | WMS | Done | 2018-07-04 | 10:55 | 12:00 | 1:05
23 | IAM | 335229 | 3 | Deploy all metadata to TECSYS |  | Andrei/Daniel | Andrei | WMS | Done | 2018-07-04 | 10:55 | 17:00 | 6:05
24 | IAM | 335229 | 5 | Deploy Mobile Equipment configuration |  | Andrei/Daniel | Andrei | WMS | Done | 2018-07-04 | 10:55 | 17:00 | 6:05
25 | IAM | 335229 | NA | Update WMS Configuration and Portal Bounce |  | Andrei/Daniel | Andrei | WMS | Done | 2018-07-04 | 1:00 | 1:02 | 0:02
26 | IAM | 335229 | 2 | Change 'System' WMS password to a secure one |  | Andrei/Daniel | NA | WMS | Pending |  |  |  | 0:00
27 | WMS | 335232 | 2 | Disable WMS SSO | Preventive measure | Andrei | Andy | WMS | NA | NA | NA | NA | NA
28 | WMS | 335232 | 7,8,9 ,10,13 | All WMS configuration (All MI, Edit with Excel, File Imports and manual steps) |  | Andrei/Daniel | Andrei | WMS | Done | 2018-07-04 | 9:38 | 12:00 | 2:22
29 | WMS | 335232 | 4,5,6 | WMS CSS, Image and javascript Deployment |  | Andrei/Daniel | EC | WMS | Done | 2018-07-04 | 9:40 | 10:10 | 0:30
30 | WMS | 335232 |  | Delete default warehosuses |  | Andrei/Daniel | DBA-SQL | WMS | Done | 2018-07-05
31 | WMS | 335232 |  | Configure 'system' user accounts setup (e.g. wms_erp_si_es) | Licenses, Roles and WMS Users | Andrei/Daniel | Andrei/Daniel | WMS | Done | 2018-07-05 | 14:00 | 15:00 | 1:00
32 | WMS | 335232 | 11 | Jasper App Server |  | Andrei/Daniel | EC | WMS | Done | 2018-07-04 | 9:40 | 10:10 | 0:30
33 | WMS | 335232 | 12 | Jasper DB |  | Andrei/Daniel | DBA-SQL | WMS | Done | 2018-07-04 | 1:40 | 1:52 | 0:12
34 | WMS | 335232 | NA | Functional Verifications |  | Andrei | NA | WMS | Done | 2018-07-04 | 1:45 | 2:10 | 0:25
35 | WMS | 335232 | NA | Warehouse options (so_f) > Document Format Name = wms_lbl_ldb |  | Andrei/Daniel | Andrei | WMS | Done | 2018-07-04 | 1:45 | 2:10 | 0:25
36 | WMS | 335232 | NA | Warehouse options (so_f) > Cycle Count Method = ITEM |  | Andrei/Daniel | Andrei | WMS | Done | 2018-07-04 | 1:45 | 2:10 | 0:25
37 | WMS | 335232 | NA | Warehouse options (so_f) > Maximum Number of Automatic Cycle Counts = X |  | Andrei/Daniel | Andrei | WMS | Done | 2018-07-04 | 1:45 | 2:10 | 0:25
38 | WMS | 335232 | NA | Stations and station devices are configured to user physical label design: |  | Andrei/Daniel | Andrei | WMS | Done | 2018-07-04 | 1:45 | 2:10 | 0:25
39 | WMS | 335232 | NA | Output Devices (md_out_device) present and able to print to corresponding physical devices (backup file – Output DevicesGOLD) |  | Andrei/Daniel | Andrei | WMS | Done | 2018-07-04 | 1:45 | 2:10 | 0:25
40 | WMS | 335232 | NA | Output Devices (md_out_device) named Zebra1 and Bullzip have been removed |  | Andrei/Daniel | Andrei | WMS | Done | 2018-07-04 | 1:45 | 2:10 | 0:25
41 | WMS | 335232 | NA | Stations (st_f) are migrated to Prod from Gold (backup file – StationGOLD) |  | Andrei/Daniel | Andrei | WMS | Done | 2018-07-04 | 1:45 | 2:10 | 0:25
42 | WMS | 335232 | NA | Station Label Devices (station_label_device) are migrated to Prod with the Document Format Name = wms_lbl_ldb or wms_lbl_so_ldb (backup file – Output DevicesGOLD) |  | Andrei/Daniel | Andrei | WMS | Done | 2018-07-04 | 1:45 | 2:10 | 0:25
43 | WMS | 335232 | NA | Document Format to External Document Maps are migrated to Prod (backup file – Document Format to External Document MapsGOLD) |  | Andrei/Daniel | Andrei | WMS | Done | 2018-07-04 | 1:45 | 2:10 | 0:25
44 | WMS | 335232 | NA | Make sure that concatenation config is completed on all hand-held devices SR #IN.RCV.BR02.SR01.03 |  | Andrei/Daniel | Andrei | WMS | Done | 2018-07-04 | 1:45 | 2:10 | 0:25
45 | WMS | 335232 | NA | Make Sure all available bar code fonts have been enabled on hand-held devices |  | Andrei/Daniel | Andrei | WMS | Done | 2018-07-04 | 1:45 | 2:10 | 0:25
46 | WMS | 335232 | NA | Connect DHW with WMS DB |  | Wendy | Wendy | WMS | Done | 2018-07-05 | 16:00 | 17:00 | 1:00
47 | Wednesday Jul 11 - Buying Guide Deployment
48 | Buying Guide | 335222 | 3 | Create XX_DDC_BG_STAGE Table in eBiz |  | Rajesh/Emily | DBA-eBiz | DCMove | Done | 2018-07-03 | 10:00 | 12:00 | 2:00
49 | Buying Guide | 335222 | 4 | BG SCDB SQL Scripts and 2 eBiz BG Grants (XXBCLDB and APPS) | Review for Production as some of the code is already there | Gabriel/Emily | DBA-Oracle | DCMove | Done | 2018-07-03 | 10:00 | 12:00 | 2:00
50 | Buying Guide | 335222 | NA | Autosys |  | NA | NA | WMS | NA | NA | NA | NA | NA
51 | Buying Guide | 335222 | 1 | Reschedule EOD to 11PM | SA to check | Emily | Operator | DCMove | Done | 2018-07-03 | 11:00 | 11:10 | 0:10
52 | Buying Guide | 335222 | 2 | Reschedule CCRS to 11:30 PM | SA to check | Gabriel/Emily | Operator | DCMove | Done | 2018-07-04 | 9:40 | 10:38 | 0:58
53 | Buying Guide | 335222 | NA | Reschedule DWH to 11PM | SA to check | Wendy/Emily | DWH | DCMove | NA | NA | NA | NA | NA
54 | Buying Guide | 335222 | NA | Schedule SC BG Cron |  | Gabriel/Emily | DBA-Oracle | DCMove | Done | 2018-07-04 | 12:12 | 13:12 | 1:00
55 | Buying Guide | 335222 | NA | Schedule BI job |  | Stanley | BI | DCMove | Done | 2018-07-04 | 9:40 | 11:22 | 1:42
56 | Buying Guide | 335222 | NA | BG BI Deployment | Verified next day by demand planners | Stanley | BI | DCMove | Done | 2018-07-04 | 9:40 | 11:22 | 1:42
57 | Buying Guide | 335222 | NA | PAR Deployment | Verified next day by demand planners | Stanley | BI | DCMove | Done | 2018-07-04 | 9:40 | 11:22 | 1:42
58 | Thursday Jul 12 - Buying Guide Verifications and IAM Interfaces Pre-Work
59 | Buying Guide | 335222 | NA | Verifiy that the new job schedules worked | EOD, CCRS, SC BG Cron (table populated) | Emily | NA | DCMove | Pending |  |  |  | 0:00
60 | Buying Guide | 335222 | NA | Verifiy that the DWH and BI job schedules worked | DWH and BI | Wendy, Stanley | NA | DCMove | NA | NA | NA | NA | NA
61 | Buying Guide | 335222 | NA | Business verifies the BG (BI) and PAR |  | Demmand planners | NA | DCMove | NA | NA | NA | NA | NA
62 | IAM | 335229 | 7 | OSB Cache Manager (Coherence) | OSB to be bounced next Sunday | Sri | DBA-Middleware | WMS | Done | 2018-07-03 | 9:20 | 12:20 | 3:00
63 | IAM | 335229 | 8 | OSB Security Settings (Support for TSL2 for WMS) | OSB to be bounced next Sunday | Sri | DBA-Middleware | WMS | Done | 2018-07-03 | 9:20 | 12:20 | 3:00
64 | IAM | 335229 | NA | Inform support centre of upcoming outages |  | James | NA | WMS | Done | NA | NA | NA | NA
65 | IAM | 335229 | NA | Endpoint Connector (disabled) to WMS via ESB Deployment | Deploy Regession/Sanity other connectors, endpoints | N8 | Developer | WMS | Done | 2018-07-05 | 15:00 | 19:00 | 4:00
66 | Sunday Jul 15 - IAM Setup
67 | Maintenance Window Starts 5 AM
68 | IAM | 335229 | 9 | OSB Bounce |  | Sri | DBA-Middleware | WMS | Done | 2018-07-03 | 12:30 | 14:30 | 2:00 |  | Check with Sherry whether we need a conference call or be on site
69 | IAM | 335229 | 10 | $U and all other steps in the SOP |  | Sri | Operator | WMS | Done | 2018-07-03 | 12:30 | 14:30 | 2:00
70 | IAM | 335229 | 10 | OSB Bounce SOP |  | Sri | DBA-Middleware | WMS | Done | 2018-07-03 | 12:30 | 14:30 | 2:00
71 | IAM | 335229 | NA | Sri to verify the MFs are working | SOAPUI, OES, iStore | Sri | NA | WMS | Done | 2018-07-03 | 15:30 | 16:00 | 0:30
72 | IAM |  |  | IDM Deploy | Migration Test to PROD Sanity tests Hide tasks - 2 roles Siteminder/SSO | N8 | Developer | WMS | Done | 2018-07-05 | 5:30 | 8:30 | 3:00
73 | Maintenance Window Ends 8 AM
74 | Monday Jul 16 - WMS Users Setup via IAM
75 | IAM | 335229 | 11 | Deploy IAM OSB Interface and all required dependencies | Deploy IAM OSB Interface and all required dependencies http://subversion.bcliquor.com/svn/SOA/Services/ESB/release/WMS/OSB/INT5-Release_Note_v3.0.5.txt Only do the section below JMS Queue for WMS Inbound transactions JMS Queue for WMS Outbound transactions JMS Queue for WMS Session ID Validator JMS Queue for WMS Inbound Status monitoring Deploy the WMS project Deploy the Cache Manager WMS Session Manager project WMS User Role Provisioning Service WMS Integration User Accounts configuration | Sri | DBA-Middleware | WMS | Done | 2018-07-04 | 9:40 | 10:52 | 1:12
76 | IAM | 335229 | NA | Sanity check the IAM OSB operations |  | Sri | NA | WMS | Done | 2018-07-04 | 10:52 | 12:00 | 1:08
77 | IAM | 335229 | NA | Advise N8 on completion |  | Sri | NA | WMS | Done | 2018-07-05 | 11:21 | 11:22 |  |  | Verify with N8 if they are okay to do this on Monday
78 | IAM | 335229 | NA | Complete Connector | Complete remaining Configuration Endpoint Explore, correlate Service Account Provisioning Role/Account Template | N8 | N8 Developer | WMS | Done | 2018-07-05 | 11:23 | 12:23 | 1:00
79 | IAM | 335229 | NA | IDM Tasks | unhide/enable access all IDM Roles FUT (end to end IAM >WMS) | N8 | N8 Developer | WMS | Done | 2018-07-05 | 12:23 | 14:23 | 2:00
80 | IAM | 335229 | NA | Verify that the 'IAM to WMS Integration' is Enabled and SSO is Ready |  | Andy | NA | WMS | Done | 2018-07-05 | NA | NA | NA
81 | IAM | 335229 | NA | Verify that the 'IAM Task' is available |  | David Campbell | NA | WMS | Done | 2018-07-05 | NA | NA | NA
82 | IAM | 335229 | NA | Configure test users in INT5 |  | David Campbell | System Security | WMS | In Progress |  |  |  | 0:00
83 | IAM | 335229 | NA | Configure real users in IAM | Make the AD users available in the IAM task (PIMMS configs) | David Campbell | System Security | WMS | In Progress |  |  |  | 0:00
84 | IAM | 335229 | NA | Verify the roles are available in IAM |  | David Campbell | NA | WMS | In Progress |  |  |  | 0:00
85 | IAM | 335229 | NA | Assigning WMS Roles to users in IAM | Could be a CR from N8 or done manual by David Campbell | David Campbell | System Security | WMS | In Progress |  |  |  | 0:00
86 | IAM | 335229 | NA | Create the SAs and Dev accounts with LDB Staging Tables roles |  | David Campbell | System Security | WMS | In Progress |  |  |  | 0:00
87 | IAM | 335229 | NA | Validate that users, stations and mobile equipment are created in WMS |  | Andrei/Daniel | NA | WMS | Done | 2018-07-04 | 13:00 | 13:10 | 0:10
88 | Thursday Jul 19 - Item Load Preparation
89 | Item Load | 335238 | NA | Confirm Doug's Ti-Hi Update File is available |  | Daniel | NA | WMS | NA | NA | NA | NA | NA
90 | Item Load | 335238 | NA | Prepare Ti-Hi Upload SQL File |  | Daniel | NA | WMS | Done | 2018-07-04 | 14:00 | 14:10 | 0:10
91 | Item Load | 335238 | NA | Inform business not to update TI/HI and Minimum Load Quantity in CPD |  | Change Mgmt, Lauren | NA | WMS | NA | NA | NA | NA | NA
92 | Item Load | 335238 | NA | Inform business not to update dimensions RB |  | Change Mgmt, Lauren | NA | WMS | NA | NA | NA | NA | NA
93 | Item Load | 335238 | 8 | Run the Ti-Hi Upload SQL File (Script) on SCProd (CPD) - include turning off and on the product msg flow trigger | No update will interface. Daniel to verify the number of update after done. | Daniel | DBA-Oracle | WMS | Done | 2018-07-05 | 16:00 |  | ?? |  | (missing 6 SKU in INT5). Daniel record lock
94 | Item Load | 335238 | NA | Communication about upcoming outage on Sunday |  | James | NA | WMS | NA | NA | NA | NA | NA
95 | Item Load | 335238 | NA | Run the query one more time on BO products for forward pick locations products | It should be clean at this point, no XPBO product for slotting | Emily/Andrei | NA | WMS | NA | NA | NA | NA | NA
96 | Sunday Jul 22 - Item Load Process
97 | Maintenance Window Starts 5 AM
98 | Item Load | 335238 | NA | Disable Item Interfaces ($U Jobs) | TSK(PM_PRDMSG_S) | Sri | EC | WMS | Done | 2018-07-05 |  |  | 0:05
99 | Item Load | 335238 | NA | Retire OSB Product MF (WOM14ab) | Retire/Disable Listeners/ProductListener_V2.0/proxy/ProductListener | Sri | DBA-Middleware | WMS | Done | 2018-07-05 |  |  | 0:05
100 | Item Load | 335238 | NA | Turn off (retire) WOM14C forever for RB | Domain: RB, BPEL Process: BCLDB_WOM_INT14_C | Sri | Sri | WMS | Done | 2018-07-05 |  |  | 0:10
101 | Item Load | 335238 | 15 | CPD .Net Application |  | Emily/Mark S. | EC | WMS | Done | 2018-07-05 |  |  | 0:05
102 | Item Load | 335238 | NA | Verify all BO products that have a forward pick location should be updated to non-BO listing type in CPD |  | Andrei/James | Business? | WMS | NA |  |  |  | 0:00 |  | James to call meeting with Business to discuss
103 | Item Load | 335238 | NA | Generate CSV for WOM14x as per instructions in "Item Volumetrics Merge" | Ti-Hi and All UOM Volumetric for all products in WMS (Verify if data looks good) | Daniel/Sri | NA | WMS | Done | 2018-07-05 |  |  | 0:10 |  | The CSV for 14x is in SVN. http://subversion.bcliquor.com/svn/WMS/Configurations/Data/releases/INT5-TST-335238/14x
104 | Item Load | 335238 | 4 | Turn off iTopia rule wms_pm_f.item_update_ldb |  | Andrei/Daniel | Andrei | WMS | Done | 2018-07-05 |  |  | 0:01
105 | Item Load | 335238 | 5 | Deploy WOM14 a/b/X OSB | - Deploy the Product Listener V2 project - Deploy the Product Listener X V2 project - Disable 14a/b Product Listener Proxy Listeners/ProductListener_V2.0/proxy/ProductListener | Sri | DBA-Middleware | WMS | Done | 2018-07-05 |  |  | 0:10
106 | Item Load | 335238 | 14 | Weblogic |  | Bhuvana | DBA-Middleware | WMS | Done | 2018-07-05 |  |  | 0:20
107 | Item Load | 335238 | 14 | JDA Service Weblogic |  | Bhuvana | DBA-Middleware | WMS | Done | 2018-07-05 |  |  | 0:00
108 | Item Load | 335238 | 14 | JDA Service Weblogic ESB Proxy |  | Bhuvana | DBA-Middleware | WMS | Done | 2018-07-05 |  |  | 0:00
109 | Item Load | 335238 | 13 | Jboss |  | Bhuvana | DBA-Middleware | WMS | Done | 2018-07-05 |  |  | 0:00
110 | Item Load | 335238 | 12 | Product Service |  | Bhuvana | DBA-Middleware | WMS | Done | 2018-07-05 |  |  | 0:00
111 | Item Load | 335238 | 13 | LDB Item Service |  | Bhuvana | DBA-Middleware | WMS | Done | 2018-07-05 |  |  | 0:00
112 | Item Load | 335238 | NA | Smoke test 14 a/b from OSB putting a payload in the product listener | all downstream systems (ebiz, LDBitem, eso, WMS) and make sure WMS 'Transferred' | Bhuvana | Bhuvana | WMS | Done | 2018-07-05 |  |  | 0:10 |  | TECsys permission problem. Added users to us_f and validated the password for wms_erp_si_es. 30 mins overall as everything is done manually
113 | Item Load | 335238 | NA | Smoke test 14X from smaller version of CSV | WMS Item load 5 item for performance test | Sri | Sri | WMS | Done | 2018-07-05 |  |  | 0:10
114 | Item Load | 335238 | NA | Take a WMS SQL DB Backup/Snapshot before loading items | All schemas | Andy | DBA-SQL | WMS | Done | 2018-07-05 |  |  | 0:05
115 | Maintenance Window Ends 8 AM
116 | Item Load | 335238 | NA | Run the Jmeter to populate the Items into TECSYS with CSV generated from "Item Volumetrics Merge" program | Creating all items in WMS by 14X (Takes 1 hr. or so) Depends on Task 100,103,109A(Argh..Ray renumber so these are outupdated see dependency column instead) SysMon and Queue Timer should be up and running. Sri to verify the pm_f load and see if there is any error in staging WMS | Sri | Sri | WMS | Done | 2018-07-06 | 15:00 | 19:00 | 4:00 | 103,105,111 | The CSV for 14x is in SVN. http://subversion.bcliquor.com/svn/WMS/Configurations/Data/releases/INT5-TST-335238/14x
117 | Monday Jul 23 - Complete Item Load Steps in WMS
118 | Item Load | 335238 | 6 | Slotting import (4 Files) |  | Andrei/Daniel | Andrei | WMS | Pending |  |  |  | 0:00 | 116 | http://subversion.bcliquor.com/svn/WMS/Configurations/Data/releases/INT5-TST-335238/File Import/ I made sure that the latest BTL3 file is included.
119 | Item Load | 335238 | NA | Functional Verifications |  | Andrei | NA | WMS | Pending |  |  |  | 0:00
120 | Item Load | 335238 | NA | Doug’s volumetrics spread sheet is complete for all CASE and BTL slotted SKUs |  | Andrei/Daniel | Andrei | WMS | Pending |  |  |  | 0:00
121 | Item Load | 335238 | NA | For five slotting files "QTY UOM 1 in UOM 2" and "QTY UOM 2 in UOM 3" are set up and matching to Doug's list |  | Andrei/Daniel | Andrei | WMS | Pending |  |  |  | 0:00
122 | Item Load | 335238 | NA | In slotting files all present SKUs are present in Prod environment |  | Andrei/Daniel | Andrei | WMS | Pending |  |  |  | 0:00
123 | Item Load | 335238 | NA | No N/A in slotting trigger and replenishment QTYs |  | Andrei/Daniel | Andrei | WMS | Pending |  |  |  | 0:00
124 | Item Load | 335238 | NA | Five slotting files are loaded in Prod environment with zero errors |  | Andrei/Daniel | Andrei | WMS | Pending |  |  |  | 0:00
125 | Item Load | 335238 | 7 | Turn on iTopia rule wms_pm_f.item_update_ldb |  | Andrei/Daniel | Andrei | WMS | Pending |  |  |  | 0:00
126 | Item Load | 335238 | NA | Run the Jmeter to populate the Items into TECSYS with second file including CPD dimensions. Only items from "Doug's List" | Updating WMS item attributes (Doug's list). iTopia will process these SKU with volumetric. Depends on task 119 | Sri | DBA-Middleware | WMS | Pending |  |  |  | 0:00
127 | Item Load | 335238 | NA | WMS item verification |  | James: Andrei/Daniel; WMS: WMS; Done: Pending; NA: 0:00
128 | Item Load | 335238 | NA | Once items are loaded with all required attributes (eg UOM, Dimension, max/min load qty ) into WMS, we need to flip Doug’s list to 'RDY'. (custom_numeric_10 = ‘1’) WMS online. The rest remains as ‘NEW | Business approval needed to proceed Depends on task 120 | Andrei/Daniel/Emily | Andrei/DBA-SQL | WMS | Pending |  |  |  | 0:00
129 | Item Load | 335238 | NA | Execute the following SQL in TecSys wms database (eg. int1_94x_w) to toggle Volumetric Changed flag to 0 to prevent WOM 14c from pulling case dimensions and TI HI back to CPD UPDATE pm_f SET custom_numeric_10 = 0 WHERE custom_numeric_10 = 1; |  | Andrei/Daniel | DBA-SQL | WMS | Pending |  |  |  | 0:00
130 | Item Load | 335238 | NA | Andrei will load Storage Rules for items in 'RDY' status | Depends on items be loaded | Andrei/Daniel | Andrei | WMS | Pending |  |  |  | 0:00
131 | Item Load | 335238 | NA | Item Technical Verifications |  | Andrei | NA | WMS | Pending |  |  |  | 0:00
132 | Item Load | 335238 | NA | Verification 1: | Once initial load is done, complete the following validation steps 1) Storage Rule checking for items in RDY status: XPBO or XCBO products should have the storage rule of SRNSWP All Status 1 products should have storage rule of 'SRSUPR' All Status 4.2 products should have storage rule of 'SRDELIST' and allow_receipt = ‘N’ 2) Verify UOM is correct 3) Query to ensure Forward Pick Location with SKU that are not 'BO' or 'Cage' product 4) Query to ensure that expire date required field for certain products as per mapping. 5) Query ‘RDY’ and ‘NEW’ status | Andrei/Daniel/Emily | Andrei | WMS | Pending |  |  |  | 0:00
133 | Item Load | 335238 | NA | Verification Step: If the queries below return no results, then we are good. The results returned need to be corrected. | --Check that XXBO products have a storage rule of SRNSWP (Ready) SELECT pm_f.sku, pm_f.sku_desc, pm_f.custom_char_2 AS ListingType, pm_f.custom_char_1 AS store_rule, pm_f.allow_rec_ret FROM pm_f WHERE 1=1 AND part_status = 'RDY' AND pm_f.whse_code = 'VDC' AND ( (pm_f.custom_char_2 like '%BO' AND store_rule != 'SRNSWP') OR (pm_f.custom_char_1 = '1.0' AND store_rule != 'SRSUPR') OR NOT (pm_f.custom_char_1 = '4.2' AND store_rule = 'SRDELIST' AND allow_rec_ret = 'N') ) | Andrei/Daniel/Emily | Andrei | WMS | Pending |  |  |  | 0:00
134 | Item Load | 335238 | NA | Verification Step: If the queries below return no results, then we are good. The results returned need to be corrected. | --Check that XXBO products have a storage rule of SRNSWP (New) SELECT pm_f.sku, pm_f.sku_desc, pm_f.custom_char_2 AS ListingType, pm_f.custom_char_1 AS store_rule, pm_f.allow_rec_ret FROM pm_f WHERE 1=1 AND part_status = 'NEW' AND pm_f.whse_code = 'VDC' AND ( (pm_f.custom_char_2 like '%BO' AND store_rule != 'SRNSWP') OR (pm_f.custom_char_1 = '1.0' AND store_rule != 'SRSUPR') OR NOT (pm_f.custom_char_1 = '4.2' AND store_rule = 'SRDELIST' AND allow_rec_ret = 'N') ) | Andrei/Daniel/Emily | Andrei | WMS | Pending |  |  |  | 0:00
135 | Item Load | 335238 | NA | Verification Step: If the queries below return no results, then we are good. The results returned need to be corrected. | --Check that XXBO and Cage are not slotted (Ready) SELECT pm_f.sku, pm_f.sku_desc, lc_f.loc, pm_f.custom_char_2 AS ListingType, pm_f.custom_char_3 AS Cage_indicator FROM pm_f, lc_f WHERE 1=1 AND (pm_f.custom_char_2 like '%BO' OR pm_f.custom_char_3 = 'Y') AND pm_f.whse_code = 'VDC' AND part_status = 'RDY' AND pm_f.sku = lc_f.sku AND pm_f.pkg = lc_f.pkg AND pm_f.whse_code = lc_f.whse_code | Andrei/Daniel/Emily | Andrei | WMS | Pending |  |  |  | 0:00
136 | Item Load | 335238 | NA | Verification Step: If the queries below return no results, then we are good. The results returned need to be corrected. | --Check that XXBO and Cage are not slotted (New) SELECT pm_f.sku, pm_f.sku_desc, lc_f.loc, pm_f.custom_char_2 AS ListingType, pm_f.custom_char_3 AS Cage_indicator FROM pm_f, lc_f WHERE 1=1 AND (pm_f.custom_char_2 like '%BO' OR pm_f.custom_char_3 = 'Y') AND pm_f.whse_code = 'VDC' AND part_status = 'NEW' AND pm_f.sku = lc_f.sku AND pm_f.pkg = lc_f.pkg AND pm_f.whse_code = lc_f.whse_code | Andrei/Daniel/Emily | Andrei | WMS | Pending |  |  |  | 0:00
137 | Item Load | 335238 | NA | Verification Step: If the queries below return no results, then we are good. The results returned need to be corrected. | --Check that Default Expiry Date is setup correctly SELECT sku, sku_desc, custom_char_6 AS ProductHierarchy, def_exp_date FROM pm_f WHERE 1=1 AND whse_code = 'VDC' AND (custom_char_6 LIKE 'Beer%' OR custom_char_6 LIKE 'Refreshment Beverages%' OR custom_char_6 LIKE 'Spirits¦Liquers¦Cream/Dairy Liqueurs') AND def_exp_date = 'Y'; | Andrei/Daniel/Emily | Andrei | WMS | Pending |  |  |  | 0:00
138 | Item Load | 335238 | NA | Verification Step: If the queries below return no results, then we are good. The results returned need to be corrected. | --Check that all products with updated dimensions are set to Ready status SELECT sku, sku_desc, part_status, wid1, hgt1, dpth1, wgt1 FROM pm_f WHERE part_status = 'NEW' AND whse_code = 'VDC' AND wid1 <> 0.99 | Andrei/Daniel/Emily | Andrei | WMS | Pending |  |  |  | 0:00
139 | Item Load | 335238 | NA | Verification Step: If the queries below return no results, then we are good. The results returned need to be corrected. | --Check that 'Ready' XXBO products have a valid storage rule ('SRNSWP','SRSUPR','SRDELIST') SELECT pm_f.sku, pm_f.sku_desc, pm_f.custom_char_2 AS ListingType, pm_f.custom_char_1 AS CPD_status, pm_f.allow_rec_ret,store_rule FROM pm_f WHERE 1=1 AND part_status = 'RDY' AND pm_f.whse_code = 'VDC' AND pm_f.custom_char_2 not like '%BO' AND store_rule in ('SRNSWP','SRSUPR','SRDELIST') | Andrei/Daniel/Emily | Andrei | WMS | Pending |  |  |  | 0:00
140 | Item Load | 335238 | NA | Verify that all CPD items are the eligible and relevant in WMS | Daniel to create a query | Daniel | NA | WMS | Pending |  |  |  | 0:00
141 | Item Load | 335238 | NA | Verify that INT5 printers are not pointing to Prod real printers |  | Andrei | NA | WMS | Pending |  |  |  | 0:00
142 | Item Load | 335238 | NA | Turn on the WOM14ab for Tecsys (Enable OSB MF and $U Job) | - Enable 14 a/b Product Listener Proxy Listeners/ProductListener_V2.0/proxy/ProductListener | Sri | DBA-Middleware | WMS | Pending |  |  |  | 0:00
143 | Item Load | 335238 | NA | Smoke test 14 a/b | -Change a SKU in CPD | Sri | Emily | WMS | Pending |  |  |  | 0:00
144 | Item Load | 335238 | NA | Run the validation tool (Tecsys) |  | James: Andrei/Daniel; NA: Andy; WMS: WMS; NA: 0:00
145 | Item Load | 335238 | NA | Execute Launch Pad A |  | James: Andrei/Daniel; NA: Andy; WMS: WMS; NA: 0:00
146 | Item Load | 335238 | NA | Change 'tecsys' and 'mitool' DB passwords | To be done after deployment | James: Andrei/Daniel; NA: DBA-SQL; WMS: WMS; NA: 0:00
147 | Item Load | 335238 | NA | Business Verifications |  | WMS: WMS; NA: 0:00
148 | Item Load | 335238 | NA | Make a change in CPD and verify in all systems | See if business wants to delegate this to IT | James: Business; NA: NA; WMS: WMS; NA: 0:00
149 | Item Load | 335238 | NA | Make a volumetrics change and change it back and verify CPD | 1 mm. up and down | James: Daniel/Emily; NA: NA; WMS: WMS; NA: 0:00
150 | Item Load | 335238 | NA | Verify that CPD volumetrics are grayed out |  | James: Daniel/Emily; NA: NA; WMS: WMS; NA: 0:00
151 | Item Load | 335238 | NA | Business Communication |  | WMS: WMS; NA: 0:00
152 | Item Load | 335238 | NA | Inform the business of the progress | Reuse the previous message | James: James; NA: NA; WMS: WMS; NA: 0:00
153 | Code Depl | 333947 | NA | Communication about upcoming outage on Sunday | Go-Live communication and communicate with Release Management | James | NA | WMS | NA | NA | NA | NA | NA
154 | Code Depl | 333947 | NA | Prepare data for sanity checks NSWP, Store Orders, Wholesale Customer Orders (Pick Order) | Data to verify that nothing goes to WMS | Doug | NA | WMS | NA | NA | NA | NA | NA
155 | Code Depl | 333947 | NA | Sales order for NSWP PO |  | WCC | NA | WMS | NA | NA | NA | NA | NA
156 | Code Depl | 333947 | NA | Prepare data for sanity checks PO | Data to verify that Vancouver POs still go to RB | Demmand planners | NA | WMS | NA | NA | NA | NA | NA
157 | Sunday Jul 29 - Final Code Migration - Interfaces, eBiz and DC Move code
158 | Maintenance Window Starts 5 AM
159 | Code Depl | 333947 | NA | $U Jobs Paused | Retire / Un-retire by DBA SOA Composites - EBS partition/ EbsPickOrderPublisher [1.2] - (WOM16 ¦ Pick Order) - JDA partition/JdaOrderPublisher [1.0] - (WOM10 ¦ Internal Replenishment) - RB partition/RbShipConfirmPublisher [1.0] - (WOM15 ¦ Ship Confirm) - TA Partition/TABatch [1.0] (TA Router) - Disable/Enable the EbizDS in JBOSS Production Disable / Enable by Operations $U [UXAPP/LDBPRD/X] - WPO_MSGFLOW_S – (wom013/wom019 ¦ PO) - WPORECEIPT_MSGFLOW_S – (wom018/wom012 ¦ PO Receipts) - PM_PRDMSG_S – (wom020/wom014 ¦ Item Update) - WOMINVADJUSTMENT_MSGFLOW_S – (wom017 ¦ Adjustment) - AL_SUBMIT_ALLOC_S - (Retail Allocation apps which calls eBiz program) - TSK(PO_MSGFLW_S)(001)(PO_MSGFLW_H)(001) - TSK(RETAIL_PO_MANAGEMENT_S)(001) - ST_MSGFLW (Sales transaction Message Flow) - AW_RECEIVE_IMPORT ( Agent Warehouse Receiving) - SL_SHLBL (Shelf Labels) WINAPP02/LDBPRD/X PL_REPORTS – VFW Price List Reports Job WINAPP03/LDBPRD/X ESO_STOCKMINLEVELS – Min Levels Job UXAPP/LDBPRD/X <No need to stop if it’s during Maintenance Window> - FD_ESO2GSA_S (ESO to GSA) | Sri | EC | WMS | NA | NA | NA | NA | NA
160 | Code Depl | 333947 |  | OSB | - Deploy the Item Ship Unit Dimension Listener project - Deploy the WMS Cancelled SalesOrder Listener - Deploy the WMS Inventory Adjustment Listener project - Deploy the WMS Outbound Listener project - Deploy the WMS Receipt Listener - Deploy the WMS ShipConfirm Listener - Deploy Wholesale Purchase Order Listener project - Deploy WMS Inventory Status Change Listener - Deploy WMS Sales Order Listener project | Sri: Sri; EC: DBA-Middleware; WMS: WMS; NA: 0:00
161 | Code Depl | 333947 |  | SOA |  | Sri: Sri; EC: DBA-Middleware; WMS: WMS; NA: 0:00
162 | Code Depl | 333947 | 20 | eBiz WOM17 | Make sure "LDB WOM-017A Inventory Adjustments from RBWMS Interface” – is not running while deploying | Emily/Rajesh | DBA-eBiz | WMS | In Progress | 2018-07-06 | 11:13 |  | -0.46736
163 | Code Depl | 333947 | 15 | Inv Adjustments .Net Application |  | Raymundo | EC | WMS | Done | 2018-07-06 | 10:53 | 11:15 | 0:22
164 | Code Depl | 333947 | 13 | Order Track Service .Net Web Service |  | Raymundo | EC | WMS | Done | 2018-07-06 | 10:53 | 11:15 | 0:22
165 | Code Depl | 333947 | 13 | RMS Service .Net Web Service |  | Raymundo | EC | WMS | Done | 2018-07-06 | 10:53 | 11:15 | 0:22
166 | Code Depl | 333947 | 13 | Puchasing Service .Net Web Service |  | Raymundo | EC | WMS | Done | 2018-07-06 | 10:53 | 11:15 | 0:22
167 | Code Depl | 333947 | 14 | New $U Deployments in disabled mode | WMS_INVADJUSTMENT_PKG WMS_PO_RECEIPT_PKG WMS_SHIP_CONFIRM_PKG WMS_ITEM_SHIP_UNIT_DIMENSION_PKG WMS_CANCEL_SALES_ORDER_PKG | Sri | EC | WMS | Done | 2018-07-05 |  |  | 0:00
168 | Code Depl | 333947 | NA | Stop (put ON-ICE) NSWP Autosys Job | PUR_sun_bopurwk_box | Emily | EC | DCMove | Done | 2018-07-06 | 11:42 | 11:47 | 0:05
169 | Code Depl | 333947 | 10, 11 | eBiz NSWP Package (WOM25 & Reports) |  | Emily/Rajesh | DBA-eBiz | DCMove | In Progress | 2018-07-06 | 11:13 |  | -0.46736
170 | Code Depl | 333947 | 18 | eBiz BG |  | Emily/Rajesh | DBA-eBiz | DCMove | In Progress | 2018-07-06 | 11:13 |  | -0.46736
171 | Code Depl | 333947 | NA | Schedule the new eBiz Buying Guide Job |  | Sri: Emily/Rajesh; EC: DBA-eBiz; WMS: DCMove; NA: 0:00
172 | Code Depl | 333947 | 16 | eBiz Lookup |  | Emily/Rajesh | DBA-eBiz | DCMove | In Progress | 2018-07-06 | 11:13 |  | -0.46736
173 | Code Depl | 333947 | 17 | eBiz Shipping Dashboards |  | Emily/Rajesh | DBA-eBiz | DCMove | In Progress | 2018-07-06 | 11:13 |  | -0.46736
174 | Code Depl | 333947 | NA | Stop OLU eBiz Concurrent Request Set | LDB Order Line Update Request Set_v1 | Emily | DBA-eBiz | DCMove | NA | NA | NA | NA | NA
175 | Code Depl | 333947 | 9 | eBiz OLU |  | Emily/Rajesh | DBA-eBiz | DCMove | In Progress | 2018-07-06 | 11:13 |  | -0.46736
176 | Code Depl | 333947 | 1 | iStore |  | Raymundo/Bikram | DBA-eBiz | DCMove | In Progress | 2018-07-06 | 11:13 |  | -0.46736
177 | Code Depl | 333947 | 2 | Postgress SQL Scripts |  | Raymundo/Wayne | DBA-PG | DCMove | Done | 2018-07-06 | 15:18 | 16:09 | 0:51
178 | Code Depl | 333947 | 3 | Inventory Visibility Data Pump Jobs |  | Raymundo/Wayne | DBA-PG | DCMove | Done | 2018-07-06 | 15:18 | 16:09 | 0:51
179 | Code Depl | 333947 | 4 | BG Datapump Job |  | Raymundo/Wayne | DBA-PG | DCMove | Done | 2018-07-06 | 15:18 | 16:09 | 0:51
180 | Code Depl | 333947 | 24 | SC DB Lookup Insert/Update |  | Raymundo/Bummoo | DBA-Oracle | DCMove | In Progress | 2018-07-06 | 15:18 |  | -0.6375
181 | Code Depl | 333947 | 22,23 | PO/RPO Generator (NSWP) |  | Raymundo/Bummoo | EC | DCMove | Done | 2018-07-06 | 11:42 | 11:53 | 0:11
182 | Code Depl | 333947 | 8 | Wholesale Inventory Service |  | Bhuvana | DBA-Middleware | WMS | Done | 2018-07-06 | 15:18 | 16:00 | 0:42
183 | Code Depl | 333947 | 19 | OES Deployment |  | Bhuvana | DBA-Middleware | WMS | Done | 2018-07-06 | 15:18 | 16:00 | 0:42
184 | Code Depl | 333947 | NA | $U Jobs Active | Retire / Un-retire by DBA SOA Composites - EBS partition/ EbsPickOrderPublisher [1.2] - (WOM16 ¦ Pick Order) - JDA partition/JdaOrderPublisher [1.0] - (WOM10 ¦ Internal Replenishment) - RB partition/RbShipConfirmPublisher [1.0] - (WOM15 ¦ Ship Confirm) - TA Partition/TABatch [1.0] (TA Router) - Disable/Enable the EbizDS in JBOSS Production Disable / Enable by Operations $U [UXAPP/LDBPRD/X] - WPO_MSGFLOW_S – (wom013/wom019 ¦ PO) - WPORECEIPT_MSGFLOW_S – (wom018/wom012 ¦ PO Receipts) - PM_PRDMSG_S – (wom020/wom014 ¦ Item Update) - WOMINVADJUSTMENT_MSGFLOW_S – (wom017 ¦ Adjustment) - AL_SUBMIT_ALLOC_S - (Retail Allocation apps which calls eBiz program) - TSK(PO_MSGFLW_S)(001)(PO_MSGFLW_H)(001) - TSK(RETAIL_PO_MANAGEMENT_S)(001) - ST_MSGFLW (Sales transaction Message Flow) - AW_RECEIVE_IMPORT ( Agent Warehouse Receiving) - SL_SHLBL (Shelf Labels) WINAPP02/LDBPRD/X PL_REPORTS – VFW Price List Reports Job WINAPP03/LDBPRD/X ESO_STOCKMINLEVELS – Min Levels Job UXAPP/LDBPRD/X <No need to stop if it’s during Maintenance Window> - FD_ESO2GSA_S (ESO to GSA) | Sri | EC | WMS | NA | NA | NA | NA | NA
185 | Code Depl | 333947 | NA | Restart Autosys OLU Jobs |  | Emily | EC | DCMove | Done | 2018-07-06 | 11:42 | 11:47 | 0:05
186 | Code Depl | 333947 | NA | Contingency if we go beyond the maintenance window |  | WMS: WMS; NA: 0:00
187 | Maintenance Window Ends 8 AM
188 | Code Depl | 333947 |  | Repush POs | Verify all POs arrive | Sri: Raymundo; EC: DBA-Middleware; WMS: WMS; NA: 0:00
189 | Code Depl | 333947 | NA | Data verification transactions are flowing | Cubiscan a real product Pallet Wrapper and Bottle Pick Tower sanity checks??? (Non liquor item, fake SO and cancel it) WOM Interfaces | Sri: Team; EC: NA; WMS: WMS; NA: 0:00
190 | Code Depl | 333947 | NA | Sanity checks |  | Sri: Team; EC: NA; WMS: WMS; NA: 0:00
191 | Code Depl | 333947 | NA | Business verifications Sales order, NSWP, OLU, Shipping Dashboards, NSWP Reports, Lookup, |  | Sri: Business; EC: NA; WMS: WMS; NA: 0:00
192 | Monday Jul 30 - Business Go-Live
193 | Business Go-Live | NA | NA | Enable SSO |  | Sri: Raymundo; EC: Andy; WMS: WMS; NA: 0:00
194 | Business Go-Live | NA | NA | On-site verification of all features |  | Sri: James; EC: NA; WMS: WMS; NA: 0:00

## Prod
Line | Phase | RLS | RLS Step | TimeSlot | Verification | Task | Details/Comments | Owner | Deployed By | Status | Date | INT5 Duration | Start | End | Dependency | Deployment Comments
1 | Pre-Requisites
2 | Pre-Reqs |  |  |  |  | RLS is being deployed communication to internal users | See RLS number on KDC RLS tab. DC, Demand planner, Vendor relations, WCC, etc. | James/Kenny | NA | Pending |  | NA
3 | Pre-Reqs |  |  |  |  | Business to confirm WMS configurations | Obtain UAT sign-off email | Craig | NA | Pending |  | NA
4 | Pre-Reqs |  |  |  |  | Business to provide location and slotting details (FIFO, FP, Storage Rule, etc) | Slotting spreadsheet | Chaminda | NA | Done |  | NA
5 | Pre-Reqs |  |  |  |  | Business to provide Locatoin mapping document ( RB -> Tecsys ) | RB location mapping to Tecsys spreadsheet | Craig | NA | In progress |  | NA
6 | Pre-Reqs |  |  |  |  | RB inventory file format for inventory load | RB inventory table format | Sri/Andrei | NA | Done |  | NA
7 | Pre-Reqs |  |  |  |  | Printer setup info ( label/laser ) | Printer name, IP addresses http://subversion.bcliquor.com/svn/WMS/Liquor/02-PROJECTS/KDC Deployment/KDC Prod Printer Names.txt | James | NA | Pending |  | NA
8 | Pre-Reqs |  |  |  |  | Business to provide printer details for auto printing shipping document | Dedicated printers for shipping document | James/Bikram | NA | Pending |  | NA
9 | Pre-Reqs |  |  |  |  | User list with role / permission | DC user spreadsheet http://subversion.bcliquor.com/svn/WMS/Liquor/02-PROJECTS/KDC Deployment/UserList Permissions for each role can be found @ http://headoffice.bcldb.com/projects/LDBDC/DC-WMS/Project%20Documents/Forms/AllItems.aspx?RootFolder=%2Fprojects%2FLDBDC%2FDC%2DWMS%2FProject%20Documents%2F20%20%2D%20Analysis%20and%20Design%2FSecurity%20Requirements&FolderCTID=0x012000E1B295AC7647614EACAF6ADA026AED15&View={6AED93DD-9495-4191-A93F-4A1E6710A39E} | Chaminda/James | NA | Done |  | NA
10 | Pre-Reqs |  |  |  |  | User mapping to mobile equipment / station / station device *** | default mobile equipment spreadsheet http://subversion.bcliquor.com/svn/WMS/Liquor/02-PROJECTS/KDC Deployment/UserList | James | Business | Done |  | NA
11 | Pre-Reqs |  |  |  |  | Loftware licences | Make sure enough loftware licenses for KDC | James | Andy | Done |  | NA
12 | Pre-Reqs |  |  |  |  | Business was notified not to make truck appointment to KDC on Feb. 27th for both PO and SO | Business approve and implement | James | Business | Done |  | NA
13 | Pre-Reqs |  |  |  |  | Ask business if it's okay to skip shipping schedule on Feb. 27 | Business confirmed SO release to warehouse at 10am and 9pm on Feb. 27 for RB to clean up all SO before deployment | James | Business | Done |  | NA
14 | Pre-Reqs |  |  |  |  | PO receiving cut off: Feb 25th, 10pm until Monday night. Blackout : Feb 26, 27 and 28th | Sri has a query to re-push those RB orders into Tecsys in case there's any PO missed. | James | Business | Done
15 | Pre-Reqs |  |  |  |  | SO: Release date cut off Feb. 24 | Confirmed with Barb that 10am orders are not dropping. 9pm orders will be dropping. However, by 9pm interfaces will be redirected to Tecsys. Sri has a query to re-push orders dropped to RB into Tecsys (in case Rb drop happened) | James | Business | Done
16 | Pre-Reqs |  |  |  |  | Ensure 10am, Feb 27th SO drop is disabled |  | James | NA | Pending |  | NA
17 | Pre-Reqs |  |  |  |  | Review if any impact to Buying Guide | There should be no impact to buying guide, as per Emily. | Emily | NA | Done |  | NA
18 | Pre-Reqs | VDC RLS |  |  |  | A list of VDC release to be deployed before KDC deployment | RLS-522372 - Update iTopia Rules to set Product Break UOM's to UOM1 value --- data fix RLS-544419 - BOL incorrect in TecSys causing potential cost to LDB | Andrei | Andrei | Pending |  | NA
19 | Pre-Reqs |  |  |  |  | Identiy KDC users to help sanity check during the production deployment | DC users to help with, . Sanity check on IAM log on to WMS KDC on Feb. 22 . Sanity check for the interfaces on Feb. 27, and they will be activated before interface deployment | Business | NA | Pending |  | NA
20 | February 22nd - Full WMS Configuration
21 | Maintenance Window Starts 8 AM
22 | WMS |  |  |  |  | Inform Business and support center for upcoming outage |  | James/Andrei | Jams/Andrei | Pending
23 | WMS |  |  |  |  | Stop $U jobs | $U [UXAPP/LDBPRD/X] - WPO_MSGFLOW_S – (wom013/wom019 ¦ PO) - PM_PRDMSG_S – (wom020/wom014 ¦ Item Update) - WMS_INV_ADJUSTMENT_S - WMS_PO_RECEIPT_S - WMS_SHIP_CONFIRM_S - WMS_ITEM_SHIP_UNIT_DIM_S - WMS_CANCEL_SALES_ORDER_S | Emily/Sri | Operators | Pending
24 | WMS |  |  |  |  | Application image backup | The nightly backup should be sufficient because there's no app server changes. The bacup takes about 5 minutes. | Andrei/Andy | EC | Pending
25 | WMS |  |  |  |  | WMS DB snapshot | prod_94x_m, prod_94x_w According to Rustem it takes about half an hour to do the DB backup. | Andrei | DBA-SQL | Pending
| WMS |  |  |  |  | Pre-requisite for MI file deployment | . Install certificate for production @ http://subversion.bcliquor.com/svn/WMS/Utilities/LDB/MiTool/releases/mi-tool-1.0/Document . Valida access to production DB | Andrei | DBA-SQL
| WMS |  |  |  |  | Add permission to wms_rt_f for the MI tool user if not yet | Grant wms_administrator CREATE and UPDATE permission to wms_rt_f | Andrei | EC
26 | WMS | 464278 | 1 |  |  | WMS configuration (All MI, Edit with Excel, File Imports and manual steps) | . Check out KDC-configuraiton files @ http://subversion.bcliquor.com/svn/WMS/Liquor/02-PROJECTS/KDC Deployment/20-MI-tools into local dir . Mitool @ http://subversion.bcliquor.com/svn/WMS/Utilities/LDB/MiTool/releases/mi-tool-1.0 . make sure system.properties and user.properties are properly set ( make sure NOT to import WmsItemMaster,WmsLocation ) . java -jar -Xms1g -Xmx1g mi-tool-1.0.jar wmsImport KDC | Andrei/Angela | DBA-SQL | Pending | [5 empty] | KDC-configuraiton files @ http://subversion.bcliquor.com/svn/WMS/Reports/branch/KDC-Configuration/ Mitool @ http://subversion.bcliquor.com/svn/WMS/Utilities/LDB/MiTool/releases/mi-tool-1.0
27 | WMS |  |  |  |  | Printer setup ( output devices ) | . Printers to configure: http://subversion.bcliquor.com/svn/WMS/Liquor/02-PROJECTS/KDC Deployment/KDC Prod Printer Names.txt . Todo: excel upload or MI-tool | Andrei/Angela | DBA-SQL | Pending
28 | WMS |  |  |  |  | Station / Station device setup | . Station/printer mapping required *** . Todo: excel upload or MI-tool | Andrei/Angela | DBA-SQL | Pending
29 | WMS |  |  |  | Y | Sanity check on WMS configuration - Run MI tool verification script | . Verify all the zone, area, section, storage rule, location, system options, carrier service, carrier station, output device, station, etc. configured successfully. Scripts to validate if rows inserted for KDC . Script @ SVN http://subversion.bcliquor.com/svn/WMS/Liquor/02-PROJECTS/KDC Deployment/20-MI-tools/MI_Load_Sanity_Check.sql . Location check is expected to fail | Sri/Andrei/Angela | NA | Pending
30 | WMS | 464278 | 2 |  |  | WMS KDC Customized configuration - SQL deployment | . Check out http://subversion.bcliquor.com/svn/WMS/Liquor/02-PROJECTS/KDC Deployment/30-SQL to local . Deploy ca_st_ldb.kdc.sql, LdbSysPropKDC.sql, PalletWrapperSetting.KDC | Andrei/Angela | DBA-SQL | Pending
#REF! | WMS |  |  |  | Y | Verify Carrier station and wms system property for KDC | . Verify carrier station is configured properly by ca_st_ldb view, check for station is the right one to use. . Verify wms system property configured for KDC, and check if the default mobile equipment type is PFRH for KDC roles. | Andrei/Angela | NA | Pending
31 | WMS | 510489 |  |  |  | Deploy all SQL DB scripts | . Check out files @ http://subversion.bcliquor.com/svn/WMS/Liquor/02-PROJECTS/KDC Deployment/30-SQL into local . Deploy rest of the files in the folder | Andrei/Angela | DBA-SQL | Pending
32 | WMS | RLS |  |  |  | WMS KDC implementation ( MD tools ) - list of RLS | . Check out files @ http://subversion.bcliquor.com/svn/WMS/Liquor/02-PROJECTS/KDC Deployment/40-MD Tools into local dir . Deploy all files in the folder | Andrei/Angela | DBA-SQL | Pending
33 | WMS |  |  |  |  | Refresh Data Dictionary and Literals in WMS to flush the cache | Tecsys -- "Refresh Data Dictionary and Literals" | Andy | EC | Pending
34 | WMS |  |  |  | Y | Sanity check the deployment for the tecsys view changes | Open some new or modified views to verify, for example, . wms_pm_f.ti_hi_ldb, . wms_ob_ord_summ_ldb, . wms_ob_ord_summ_loader_view_ldb, . wms_v_ob_ord_stt_summ_ldb, . wms_v_ob_stager_view_ldb . wms_wv_f.wave_mgmt | Andrei | NA | Pending
35 | WMS |  |  |  |  | Communicate with business/VDC about WMS restart |  | James | NA | Pending
36 | WMS |  |  |  |  | Restart WMS portal | Restart sys_mon and validate the timers are running | Andy | EC | Pending
37 | WMS |  |  |  |  | Restart Iguana service |  | Andy | EC | Pending
38 | WMS |  |  |  | Y | Functional Verifications |  | Andrei/Angela | NA | Pending
39 | WMS |  |  |  | Y | Warehouse options (so_f) > Document Format Name = wms_lbl_ldb | Validate document format setup in warehouse options | Andrei/Angela | NA | Pending
40 | WMS |  |  |  | Y | Warehouse options (so_f) > Cycle Count Method = ITEM | Validate cycle count method setup in warehouse options | Andrei/Angela | NA | Pending
41 | WMS |  |  |  | Y | Warehouse options (so_f) > Maximum Number of Automatic Cycle Counts = 20 | Validate Maximum Number of Automatic Cycle Counts setup in warehouse options | Andrei/Angela | NA | Pending
42 | WMS |  |  |  | Y | Output Devices (md_out_device) present and able to print to corresponding physical devices | . Validate with printer config matrix @ http://subversion.bcliquor.com/svn/WMS/Liquor/02-PROJECTS/KDC Deployment/KDC Prod Printer Names.txt | Andrei/Angela | NA | Pending
42 | WMS |  |  |  | Y | Stations and station devices are configured to user physical label design | . Validate against station/device spreadsheet @ http://subversion.bcliquor.com/svn/WMS/Liquor/02-PROJECTS/KDC Deployment/UserList . Validate no testing printer names in use, such as Bullzip . Validate Station Label Devices (station_label_device) are migrated to Prod with the Document Format Name = wms_lbl_ldb or wms_lbl_so_ldb | Andrei/Angela | NA | Pending
#REF! | WMS |  |  |  | Y | Output Devices (md_out_device) named for testing, eg. Bullzip have been removed |  | Andrei/Angela | NA | Pending
#REF! | WMS |  |  |  | Y | Make sure that concatenation config is completed on all hand-held devices |  | Business | NA | Pending
#REF! | WMS |  |  |  | Y | Make Sure all available bar code fonts have been enabled on hand-held devices |  | Business | NA | Pending
#REF! | WMS |  |  |  | Y | Make sure scanning mobile devices are configured for Prod - SDK installed, data wedge imported and installed, server configuration pointing to Prod server |  | Business | NA
#REF! | WMS |  |  |  |  | Start $U jobs | $U [UXAPP/LDBPRD/X] - WPO_MSGFLOW_S – (wom013/wom019 ¦ PO) - PM_PRDMSG_S – (wom020/wom014 ¦ Item Update) - WMS_INV_ADJUSTMENT_S - WMS_PO_RECEIPT_S - WMS_SHIP_CONFIRM_S - WMS_ITEM_SHIP_UNIT_DIM_S - WMS_CANCEL_SALES_ORDER_S | Andrei | Operators | Pending
#REF! |  |  |  |  | Y | Check if any stuck message for re-push | This is for OSB, SOA, Ebiz staging, RB | Sri/Emily | NA
#REF! | WMS |  |  |  | Y | Regression check on VDC | **Business to validate . Inbound receiving/putaway . Outbound wave planning/pick . Inventory replenishment | Doug | NA | Pending
#REF! | Februray 22nd - WMS KDC Users Setup via IAM
#REF! | IAM |  |  |  |  | Grant integration users access to KDC : iamaccount and wms_erp_si_es | Login into TECSYS - Create the WMS Interface Users for KDC - Go to WMS Users Screen (wms_us_f) - Create a new Entry for KDC warehouse for the user 'wms_erp_si_es' - Warehouse: KDC - Username: wms_erp_si_es - Default Warehouse: No - Warehouse Authorization Level: 2 - Full - Default Station: BASE - Default Mobile Equipment Type: PFRH - Interrupt Picking: 1 - No - Verification Authorization: 0 - None - Create a new Entry for KDC warehouse for the user 'iamaccount' - Warehouse: KDC - Username: iamaccount - Default Warehouse: No - Warehouse Authorization Level: 2 - Full - Default Station: BASE - Default Mobile Equipment Type: PFRH - Interrupt Picking: 1 - No - Verification Authorization: 0 - None - Clean the md_session for the user and force them to login again - Go to Session (meta_md_session) screen - Search for user 'wms_erp_si_es' with the criteria below - User Name: wms_erp_si_es - Termination Action: 0 - Session Type: 3 - Select all the active session and use the "Terminate Session" under the hamburger menu to terminate - Search again to makesure all the active sessions are terminated | Andy | EC | Pending
#REF! | IAM |  |  |  |  | Verify that the 'IAM to WMS Integration' is working by configuring a user |  | Andy | NA | Pending |  | NA
#REF! | IAM |  |  |  |  | Configure KDC users in IAM | . Make the AD users available in the IAM task (PIMMS configs) . About 104 KDC users | David Campbell | System Security | Done
#REF! | IAM |  |  |  |  | Verify the roles are available in IAM | All WMS roles should be available in IAM | Andrei | NA | Pending
#REF! | IAM |  |  |  |  | Assigning WMS Roles to KDC users in IAM | Assigne user roles based on user role spreadsheet *** http://subversion.bcliquor.com/svn/WMS/Liquor/02-PROJECTS/KDC Deployment/UserList | DC Managers/David Campbell Chaminda | System Security | Pending
#REF! | IAM |  |  |  | Y | Validate that users, stations and mobile equipment are created in WMS | Verify users are setup properly in WMS according to the KDC user roles spreadsheet, . md_user . us_f . md_user_license | Andrei | NA | Pending
#REF! | IAM |  |  |  | Y | Sanity check on user setup | Verify new KDC users can login to WMS successfully with the right default station and mobile equipment ** Need help from a KDC user to log in, name? | Andrei | NA | Pending
#REF! | IAM |  |  |  |  | Communicate to business for disabling KDC users in Tecsys for cut-over | Email to Glen Firman, Doug McDonald, John Sweet, Ken McDonnell, David Campbell, Hector Wong | James | NA
#REF! | IAM |  |  |  |  | Disable all KDC users in Tecsys | Check out script to bulk disable all KDC only users from SVN http://subversion.bcliquor.com/svn/WMS/Liquor/02-PROJECTS/KDC Deployment/UserList . DisableKDCusers.sql | Andrei | SQL-DBA
#REF! | IAM |  |  |  | Y | Sanity check that KDC users are disable | User login would show "The account has been deactivated" ** Need help from a KDC user to log in, name? | Andrei
#REF! | Februray 22nd - KDC Item Setup, Slotting and Item Interface
#REF! | Item Load |  |  |  |  | Inform Business | Inform business - Not to update any items in TECSYS (DC) - Iguana interface will be stoped so no cubic scanning (DC) - Item interface will be stopped so item change in CPD will not be synced (Demand Planner, Vendor Relations, Cannabis) | James/Andrei | Jams/Andrei | Pending
#REF! | Item Load | 432557 | 2 |  |  | Disable Item jobs and tasks | WOM014A/B/C $U - PM_PRDMSG_S - WMS_ITEM_SHIP_UNIT_DIM_S Iguana Interface - CubiScan100 to WMS - CubiScan150 to WMS Itopia rule -wms_pm_f.item_update_ldb | Sri/Emily | Operators/Andy/Sri/Emily | Pending
#REF! | Item Load | 432557 | 2 |  |  | Prerequisite to proceed | Steps: - All storage rules are in place, in particular --SRSUPR --SRNSWP --SRDELIST - Check and recover any failed transactions from the interfaces below - Item - WOM14A/B - Volumetric WOM14C (custom_numeric_10 = 1) - Cubic Scan WOM14D Check the WMS staging table for item to be sure no stuck transactions. If any stuck, recover it. | Sri/Andrei | Sri/Emily/Andrei | Pending
#REF! | Item Load | 432557 | 2 |  |  | Get the DBAs to backup the content of pm_f & al_f tables, skip if done by previous step | DB: WMS Schema: prod_94x_w Back up the prod_94x_w schema so if needed we can use it to do rollbadk Share the temp table names with Sri/Emily | Sri | DBA/Sri | Pending
#REF! | Item Load |  |  |  |  | Integration User Setup if not done in previous step | Give User 'wms_erp_si_es' and 'iamaccount' access to KDC warehouse
#REF! | Item Load | 432557 | 2 |  |  | Run the scrip to copy VDC Item to KDC Fix Break UOM as needed for item in KDC | Run this script again TECSYS WMS DB to copy VDC Item into KDC - DB: tswmsdb - Schema:prod_94x_w - Script: http://subversion.bcliquor.com/svn/WMS/Reports/branch/KDC-Project/RLS-432557/KDC_Initial_Load.sql | Sri/Emily/Andrei | SQL-DBA | Pending
#REF! | Item Load |  |  |  |  | Check and update Break UOM = UOM1 |  | Sri | SQL-DBA
#REF! | Item Load | 432557 | 2 |  | Y | Sanity Check the initial load | Run this script section by section again TECSYS WMS DB and compary the output to expected output - DB: tswmsdb - Schema:prod_94x_w - Script: http://subversion.bcliquor.com/svn/WMS/Reports/branch/KDC-Project/RLS-432557/Sanity_Check.sql | Sri/Emily/Andrei | Sri/Emily/Andrei | Pending
#REF! | Item Load | 464278 |  |  |  | Import all locations with slotting details including FP setup | . KDC-configuraiton files should have checked out @ http://subversion.bcliquor.com/svn/WMS/Liquor/02-PROJECTS/KDC Deployment/20-MI-tools into local dir . Mitool @ http://subversion.bcliquor.com/svn/WMS/Utilities/LDB/MiTool/releases/mi-tool-1.0 . make sure system.properties and user.properties are properly set ( WmsLocation only ) . java -jar -Xms1g -Xmx1g mi-tool-1.0.jar wmsImport KDC | Andrei | Andrei
#REF! | Item Load |  |  |  | Y | MI tool sanity check script | There should not have any error reported. Add checking for break UOM.
#REF! | Item Load |  |  |  | Y | Functional Verifications |  |  | NA | Pending
#REF! | Item Load |  |  |  | Y | In slotting files all present SKUs are present in Prod environment | Verify the number of FP with item is the same as the slotting spreadsheet*** . This may be done in MI validation | Andrei | Andrei | Pending
#REF! | Item Load |  |  |  |  | Setting up items with storage rule and status | ***Business approved by Glen through email*** . Once items are loaded with all required attributes (eg UOM, Dimension, max/min load qty ) into WMS, flip KDC slotted items to 'RDY'. . Bulk change through LDB Items Load view: wms_pm_f.load_ldb to set storage rule and 'RDY' status for the slotted items . The rest remains as ‘NEW'. | Andrei | Andrei/DBA-SQL | Pending
#REF! | Item Load | 432557 | 3 |  |  | Deploy the Item - Itopia Rule | Download the MD tool from: •http://subversion.bcliquor.com/svn/WMS/Reports/branch/KDC-Project/RLS-432557/MD-Tool - 70 - Rules - wms_pm_f.item_update_ldb - PROD.xlsm •http://subversion.bcliquor.com/svn/WMS/Reports/branch/KDC-Project/RLS-432557/MD-Tool - 70 - Rules - wms_pm_f.item_update_ldb.xlsm Steps to delete the old rule: 1) Open previously download MD too file "MD-Tool - 70 - Rules - wms_pm_f.item_update_ldb - PROD.xlsm" and update the application and metadata location to PROD. 2) Delete the old view using the "Delete Subject" button on the MD tool. Step to create the new rule: 1) Open previously download MD too file "MD-Tool - 70 - Rules - wms_pm_f.item_update_ldb.xlsm" and update the application and metadata location to PROD. 2) Create/Update the view using "Update Subject" button on the MD tool | Sri | SQL-DBA/Sri | Pending
#REF! | Item Load | 432557 | 5 |  |  | Deploy the Items - Extract Volumetric view | Download the MD tool from: •http://subversion.bcliquor.com/svn/WMS/Reports/branch/KDC-Project/RLS-432557/MD-Tool - 10 - View - Items - Extract Volumetric - PROD.xlsm •http://subversion.bcliquor.com/svn/WMS/Reports/branch/KDC-Project/RLS-432557/MD-Tool - 10 - View - Items - Extract Volumetric.xlsm Steps to delete the old view: 1) Open previously download MD too file "MD-Tool - 10 - View - Items - Extract Volumetric - PROD.xlsm" and update the application and metadata location to PROD. 2) Delete the old view using the "Delete Subject" button on the MD tool. Step to create the new view: 1) Open previously download MD too file "MD-Tool - 10 - View - Items - Extract Volumetric.xlsm" and update the application and metadata location to PROD. 2) Create/Update the view using "Update Subject" button on the MD tool | Sri | SQL-DBA/Sri | Pending
#REF! | Item Load | 432557 | 9 |  |  | Deploy the Items - Item Interface view | Download the MD tool from: http://subversion.bcliquor.com/svn/WMS/Reports/branch/KDC-Project/RLS-432557/MD-Tool - 11 - View - Items - SI_ES_LDB.xlsm Step to create the new view: 1) Open previously download MD too file "MD-Tool - 11 - View - Items - SI_ES_LDB.xlsm" and update the application and metadata location to PROD. 2) Create/Update the view using "Update Subject" button on the MD tool | Sri
#REF! | Item Load |  |  |  | Y | Sanity check if deployed successfully | Visual check the changes are properly deployed, . the itopia rule wms_pm_f.item_update_ldb . wms_pm_f.extract_volumetric_es view . wms_pm_f.item_si_es_ldb view | Sri |  | Pending
#REF! | Item Load |  |  |  |  | Enable item itopia rule | Enable wms_pm_f.item_update_ldb | Sri
#REF! | Item Load | 432557 | 10 |  |  | Refresh Data Dictionary and Literals in WMS to flush the cache | Tecsys -- "Refresh Data Dictionary and Literals" | Sri |  | Pending
#REF! | Item Load |  |  |  | Y | Sanity check the view deployed successfully | wms_pm_f.extract_volumetric_es wms_pm_f.item_si_es_ldb | Sri |  | Pending
#REF! | Item Load |  |  |  | Y | Run the validation tool (Tecsys) | Tecsys to provide | Sri/Andrei | Andy | Pending
#REF! | Item Load |  |  |  | Y | Item Technical Verifications |  | Andrei | NA | Pending
#REF! | Item Load |  |  |  | Y | Verification 1: | Once initial load is done, complete the following validation steps 1) Storage Rule checking for items in RDY status: All Status 1 products should have storage rule of 'SRSUPR' All Status 4.2 products should have storage rule of 'SRDELIST' 2) Verify UOM is correct 3) Query to ensure Forward Pick Location with SKU that are not 'BO' or 'Cage' product 4) Query ‘RDY’ and ‘NEW’ status | Andrei/Sri/Emily | Andrei | Pending
#REF! | Item Load |  |  |  | Y | Verification Step: If the queries below return no results, then we are good. The results returned need to be corrected. | --Check that XXBO products have a storage rule of SRNSWP (Ready) SELECT pm_f.sku, pm_f.sku_desc, pm_f.custom_char_2 AS ListingType, pm_f.custom_char_1 as item_status, store_rule, pm_f.allow_rec_ret FROM pm_f WHERE 1=1 AND part_status = 'RDY' AND pm_f.whse_code = 'KDC' AND ( (pm_f.custom_char_2 like '%BO' AND store_rule NOT IN ('SRNSWP', 'SRDELIST')) OR (pm_f.custom_char_1 = '1.0' AND pm_f.custom_char_2 not like '%BO' AND store_rule != 'SRSUPR') ) OR (pm_f.custom_char_1 = '4.2' AND store_rule NOT IN ('SRDELIST', 'SRNSWP', 'SRSUPR') ) | Andrei/Sri/Emily | Andrei | Pending
#REF! | Item Load |  |  |  | Y | Verification Step: If the queries below return no results, then we are good. The results returned need to be corrected. | --Check that XXBO products have a storage rule of SRNSWP (New) SELECT pm_f.sku, pm_f.sku_desc, pm_f.custom_char_2 AS ListingType, pm_f.custom_char_1 as item_status, store_rule, pm_f.allow_rec_ret FROM pm_f WHERE 1=1 AND part_status = 'NEW' AND pm_f.whse_code = 'KDC' AND ( (pm_f.custom_char_2 like '%BO' AND store_rule != 'SRNSWP') OR (pm_f.custom_char_1 = '1.0' AND pm_f.custom_char_2 not like '%BO' AND store_rule != 'SRSUPR') OR (pm_f.custom_char_1 = '4.2' AND store_rule != 'SRDELIST' ) ) | Andrei/SriEmily | Andrei | Pending
#REF! | Item Load |  |  |  | Y | Verification Step: If the queries below return no results, then we are good. The results returned need to be corrected. | --Check that XXBO and Cage are not slotted (Ready) SELECT pm_f.sku, pm_f.sku_desc, lc_f.loc, pm_f.custom_char_2 AS ListingType, pm_f.custom_char_3 AS Cage_indicator FROM pm_f, lc_f WHERE 1=1 AND (pm_f.custom_char_2 like '%BO' OR pm_f.custom_char_3 = 'Y') AND pm_f.whse_code = 'KDC' AND part_status = 'RDY' AND pm_f.sku = lc_f.sku AND pm_f.pkg = lc_f.pkg AND pm_f.whse_code = lc_f.whse_code | Andrei/Sri/Emily | Andrei | Pending
#REF! | Item Load |  |  |  | Y | Verification Step: If the queries below return no results, then we are good. The results returned need to be corrected. | --Check that XXBO and Cage are not slotted (New) SELECT pm_f.sku, pm_f.sku_desc, lc_f.loc, pm_f.custom_char_2 AS ListingType, pm_f.custom_char_3 AS Cage_indicator FROM pm_f, lc_f WHERE 1=1 AND (pm_f.custom_char_2 like '%BO' OR pm_f.custom_char_3 = 'Y') AND pm_f.whse_code = 'KDC' AND part_status = 'NEW' AND pm_f.sku = lc_f.sku AND pm_f.pkg = lc_f.pkg AND pm_f.whse_code = lc_f.whse_code | Andrei/Sri/Emily | Andrei | Pending
#REF! | Item Load |  |  |  | Y | Verification Step: If the queries below return no results, then we are good. The results returned need to be corrected. | --Check that Default Expiry Date is setup correctly SELECT sku, sku_desc, custom_char_6 AS ProductHierarchy, def_exp_date FROM pm_f WHERE 1=1 AND whse_code = 'KDC' AND (custom_char_6 LIKE 'Beer%' OR custom_char_6 LIKE 'Refreshment Beverages%' OR custom_char_6 LIKE 'Spirits¦Liquers¦Cream/Dairy Liqueurs') AND def_exp_date = 'Y'; | Andrei/Daniel/Emily | Andrei | Pending
#REF! | Item Load |  |  |  | Y | Verification Step: If the queries below return no results, then we are good. The results returned need to be corrected. | --Check that all products with updated dimensions are set to Ready status SELECT sku, sku_desc, part_status, wid1, hgt1, dpth1, wgt1 FROM pm_f WHERE part_status = 'NEW' AND whse_code = 'KDC' AND wid1 <> 0.99 | Andrei/Daniel/Emily | Andrei | Pending
#REF! | Item Load |  |  |  | Y | Verification Step: If the queries below return no results, then we are good. The results returned need to be corrected. | --Check that 'Ready' XXBO products have a valid storage rule ('SRNSWP','SRSUPR','SRDELIST') SELECT pm_f.sku, pm_f.sku_desc, pm_f.custom_char_2 AS ListingType, pm_f.custom_char_1 AS CPD_status, pm_f.allow_rec_ret,store_rule FROM pm_f WHERE 1=1 AND part_status = 'RDY' AND pm_f.whse_code = 'KDC' AND pm_f.custom_char_2 not like '%BO' AND store_rule in ('SRNSWP','SRSUPR','SRDELIST') | Andrei/Sri/Emily | Andrei | Pending
#REF! | Item Load | 432557 | 4 |  |  | Make sure the Product Service V5 already in Production | Bhuvana to confirm | Bhuvana |  | Pending
#REF! | [5 empty] | Add the Email Notification records for item interface | Download http://subversion.bcliquor.com/svn/SOA/ESB/tags/RLS_432557_WMS_Liquor_KDC_Release/Deploy/Notification/prod.sql Login to the DB and execute the script ( ONLY the INSERT statement ) DB: RTINVP SCHEMA: SOA_AUDIT | Sri | DBA
#REF! | [5 empty] | Deploy item interface | Deploy the OSB projects - Login to the SBConsole and create a session - Deploy the WMS project - Download the project from http://subversion.bcliquor.com/svn/SOA/ESB/tags/RLS_432557_WMS_Liquor_KDC_Release/Deploy/WMS/WMS_1.1.0.jar - Import the project using OSB sbconsole with advanced settings to preserve both the operational and security settings - Deploy the ProductListener - Download the project from http://subversion.bcliquor.com/svn/SOA/ESB/tags/RLS_432557_WMS_Liquor_KDC_Release/Deploy/ProductListener_V3.0/ProductListener_V3.0.2_WMS_patch.jar - Import the project using OSB sbconsole with advanced settings to preserve both the operational and security settings - Deploy the ItemShipUnitDimensionListener - Download the project from http://subversion.bcliquor.com/svn/SOA/ESB/tags/RLS_432557_WMS_Liquor_KDC_Release/Deploy/ItemShipUnitDimensionListener/ItemShipUnitDimensionListener_1.0.0.jar - Download the customization file from http://subversion.bcliquor.com/svn/SOA/ESB/tags/RLS_432557_WMS_Liquor_KDC_Release/Deploy/ItemShipUnitDimensionListener/PROD_ItemShipUnitDimensionListener_CustomizationFile_1.0.0.xml - Delete project Listeners/ItemShipUnitDimensionListener - Import the project and execute the customization file using OSB console - Deploy the WMSInboundStatusMonitor - Download the project from http://subversion.bcliquor.com/svn/SOA/ESB/tags/RLS_432557_WMS_Liquor_KDC_Release/Deploy/WMSInboundStatusMonitor/WMSInboundStatusMonitor_1.0.0.jar - Download the customization file from http://subversion.bcliquor.com/svn/SOA/ESB/tags/RLS_432557_WMS_Liquor_KDC_Release/Deploy/WMSInboundStatusMonitor/PROD_WMSInboundStatusMonitor_CustomizationFile_1.0.0.xml - Delete project Listeners/WMSInboundStatusMonitor - Import the project and execute the customization file using OSB console | Sri | DBA-Middleware
#REF! | Item Load |  |  |  | Y | Sanity check OSB deployment | make sure all OSB projects' codes are deployed successfully | Sri/Emily |  | Pending
#REF! | Item Load |  |  |  | Y | Sanity check 14A/B/C |  | Sri/Emily/business |  | Pending
#REF! | Item Load |  |  |  |  | Enable Item jobs | Itopia rule -wms_pm_f.item_update_ldb Iguana Interface - CubiScan100 to WMS - CubiScan150 to WMS - New WOM014A/B and WOM014C should be deployed before turning on the $U jobs below so any changed to product or volumetric is synced to both warehouse. WOM014A/B/C $U - PM_PRDMSG_S - WMS_ITEM_SHIP_UNIT_DIM_S Inform business they can start updating Items in TECSYS until this is completed | N/A | Operators/Sri/Emily | Pending
#REF! | Item Load |  |  |  | Y | Make a change in CPD and verify in all systems | See if business wants to delegate this to IT . Make a product change, eg. volumetrics change 1 mm. up and down and change it back and verify CPD and tecsys VDC/KDC . Make a UPC/SCC change and change it back and verify Tecsys VDC/KDC | Sri/Emily/Andrei | Business/emily | Pending
#REF! | Item Load |  |  |  | Y | Data verification transactions are flowing | Cubiscan a real product, changes go to both VDC and KDC in tecsys pm_f | Sri/Emily/Andrei
#REF! | Item Load |  |  |  |  | Inform Business | Inform business - Can start updating items in TECSYS (DC) - Iguana interface is started so so can start cubic scanning (DC) - Item interface is started up so item change in CPD will be synced, (Demand Planner, Vendor Relations, Cannabis) | James/Andrei | Jams/Andrei | Pending
#REF!
#REF! | Maintenance Window Ends 4 PM
#REF! | Februray 27 - Pre-deployment
#REF! | Pre-deploy |  |  |  |  | Communicate with external/internal users/support center for the upcoming outage due to system upgrade | . no appointment of inbound/outbound trucks to KDC on Feb. 27 . no SO release to RB on Feb. 27 ( 10 am drop should be cancelled from Ebiz ) | James | NA | Pending
#REF! | Pre-deploy |  |  | 6:30AM |  | Radio Beacon cleanup - IT details By Wendy *** All orders has to be either not started or completed in RB, no half way orders in the system | By 2:30pm . Business receipt close out all PO in RB . Business ship complete all SO in RB . Business clear all pending returns /RTV closed out / pending inventory adjustment in RB | Wendy/Business | Wendy | Pending
#REF! | Pre-deploy |  |  |  | Y | Business to clean up the virtual location/hash bin in RB - IT details By Wendy | Script to validate ? | Wendy/Business | Wendy | Pending
#REF! | Pre-deploy |  |  | 2:00PM | Y | Clear any stuck transactions/messages | . Verify all PO receipt and SO ship confirm in RB successful in SCINTERFACE . Script to run, still need script for PO select delivery_id, status_name, initial_pickup_date from apps.WSH_NEW_DELIVERIES_V@finp1 where 1=1 and delivery_id in ( select distinct delivery_id from scinterface.PICK_ORDER_HEAD where whse_id = 'K' and trunc(released_date) > '31-DEC-2018') and upper(status_name) = 'OPEN' . Repush stuck transactions | Wendy/Sri | DBA | Pending
#REF! | Pre-deploy | [7 empty] | NA | Pending
#REF! | Pre-deploy |  |  | 2:30PM - 6:00PM |  | Business to complete inventory adjustment in RB for FP based on cycle count result | All inventory in RB maps to physical locations which have mapping in Tecsys | Business | NA | Pending
#REF! | Pre-deploy |  |  |  | Y | Check all inventory adjustment messages flow to Ebiz | Wendy to manual check | Wendy | DBA
#REF! | Pre-deploy |  |  | 6:30PM |  | Cut down RB connection and user access | . Offline file watcher . Script to disable all KDC users in RB select * into ivc_rbeacon.dbo.PASSWORD_PROD_BK from [rbwmsdb.bcldb.com\radiobeacon].prod_rbeacon.dbo.[PASSWORD] update [prod_rbeacon].[dbo].[PASSWORD] set PRIVILEGE = 0, ISADMIN = 0 | Wendy | DBA
#REF! | Pre-deploy |  |  | 6:30PM |  | Double check for failed/stuck transctions in interfaces | . Script to find outstanding KDC purchase orders . Script to find outstanding KDC sales orders . Scripts @ http://subversion.bcliquor.com/svn/WMS/Reports/branch/KDC-Project/RLS-432557/Cutover_Repush_Sctipt.sql and http://subversion.bcliquor.com/svn/WMS/Reports/branch/KDC-Project/RLS-432557/SO_Repush_Compare.xlsx | Emily/Sri | Emily/Sri | Pending
#REF! | Pre-deploy | [8 empty] | Pending
#REF! | Februray 27 - Inventory Setup
#REF! | Maintenance Window Starts PM
#REF! | Inv Load |  |  |  |  | Inform business |  | James | NA | Pending
#REF! | Inv Load |  |  |  |  | Double check and make sure the inv up table are empty | script to check KDC up_f, up_ship, up_receipt select count(*) from up_f where whse_code = 'KDC' | Sri | Sri | Pending
#REF! | Inv Load |  |  | 6:30PM |  | Extract from RB for the inventory and use mapping file | inventory files with the extracted RB stock data | Adrei/Wendy |  | Pending
#REF! | Inv Load |  |  | 6:45PM |  | $U Jobs Paused | $U [UXAPP/LDBPRD/X] - WMS_INV_ADJUSTMENT_S - PM_PRDMSG_S – (wom020/wom014 ¦ Item Update) - Product status change
#REF! | Inv Load |  |  | 7:00PM |  | Import RB Inventory to Tecsys |  | Adrei/Wendy |  | Pending
#REF! | Inv Load | [8 empty] | Pending
#REF! | Inv Load |  |  |  | Y | Verify the consistancy between iv_f imported, lc_f Empty = N, pm_f Item Status = RDY | Run the verification script @ SVN which returns all inventory not imported and in stock items do not have FPs assigned (ideally should return no errors). If errors occur - fix errors in RB and run this step once again Add the script | Adrei | NA | Pending
#REF! | Inv Load |  |  |  |  | Inform the business of the progress | Reuse the previous message. Inform Finance of the inventory import variances | James | NA | Pending
#REF! | [5 empty] | Inform the business of the inventory import errors | Allow business to fix the inventory import errors in RB Activate RB users with the script (Wendy to provide the script)
#REF! | [5 empty] | Disable RB users after completing the inventory import | Copy the disable RB users script in here select * into ivc_rbeacon.dbo.PASSWORD_PROD_BK from [rbwmsdb.bcldb.com\radiobeacon].prod_rbeacon.dbo.[PASSWORD] update [prod_rbeacon].[dbo].[PASSWORD] set PRIVILEGE = 0, ISADMIN = 0
#REF! | [5 empty] | Enable $U Jobs | $U [UXAPP/LDBPRD/X] - PM_PRDMSG_S – (wom020/wom014 ¦ Item Update)
#REF! | Februray 27 - Interfaces Deployment
#REF! | Maintenance Window Starts PM
#REF! | I/F Depl |  |  |  |  | Inform support centre and business of upcoming outages |  | James | NA | Pending |  | NA
| I/F Depl |  |  |  |  | Enable access for KDC users to do business sanity check | Identiy KDC users to do business sanity check Doug and Glen admin access
#REF! | I/F Depl |  |  |  |  | make sure no stuck transaction in the interfaces, and recover the failed ones | RB, OSB, SOA, Ebz staging Should have been checked in previous step, double check here. | Sri/Emily |  | Pending
#REF! | I/F Depl |  |  | 6:30PM |  | $U Jobs Paused | $U [UXAPP/LDBPRD/X] - WPO_MSGFLOW_S – (wom013/wom019 ¦ PO) - PM_PRDMSG_S – (wom020/wom014 ¦ Item Update) - WMS_INV_ADJUSTMENT_S - WMS_PO_RECEIPT_S - WMS_SHIP_CONFIRM_S - WMS_ITEM_SHIP_UNIT_DIM_S - WMS_CANCEL_SALES_ORDER_S | Sri | EC | Pending |  | NA
#REF! | I/F Depl | 432557 | 1 | 7:15PM |  | Integration User Setup, skip if already setup in previous step | Give User 'wms_erp_si_es' and 'iamaccount' access to KDC warehouse | Sri | Sri/WMS Admin | Pending | [5 empty] | Please refer to KDC interface release note for detailed steps: http://subversion.bcliquor.com/svn/SOA/ESB/tags/RLS_432557_WMS_Liquor_KDC_Release/Deploy/PROD-Release_Note_v1.0.0.txt
#REF! | I/F Depl | 432557 | 1 |  |  | Sanity check user setup | make sure the above user can access KDC | Sri |  | Pending
#REF! | I/F Depl | 432557 | 1 | 7:30PM |  | SOA email notification setup | Added the Email Notification records *** update statement for Inevntory adjustment only @ http://subversion.bcliquor.com/svn/SOA/ESB/tags/RLS_432557_WMS_Liquor_KDC_Release/Deploy/Notification/prod.sql | Sri | SQL-DBA/Sri | Pending
#REF! | I/F Depl | 432557 | 1 | 7:45PM |  | OSB deployment | - Deploy the WMSInventoryAdjustmentListener | Sri | DBA-Middleware | Pending | [5 empty] | Please refer to KDC interface release note for detailed steps: http://subversion.bcliquor.com/svn/SOA/ESB/tags/RLS_432557_WMS_Liquor_KDC_Release/Deploy/PROD-Release_Note_v1.0.0.txt
#REF! | I/F Depl | 432557 | 1 |  |  | SOA deployment | Do the deployments below : - Deploy EbsInventoryAdjustmentsSubscriber | Sri | DBA-Middleware | Pending | [5 empty] | Please refer to KDC interface release note for detailed steps: http://subversion.bcliquor.com/svn/SOA/ESB/tags/RLS_432557_WMS_Liquor_KDC_Release/Deploy/PROD-Release_Note_v1.0.0.txt
#REF! | I/F Depl | 432557 | 1 |  | Y | code validation on OSB and SOA deployment | . Make sure all OSB projects' codes are deployed successfully . Make sure inventory adjustment data flow as expected for both VDC and KDC | Sri/Emily |  | Pending
#REF! | I/F Depl |  |  |  |  | Enable $U Jobs | $U [UXAPP/LDBPRD/X] - WMS_INV_ADJUSTMENT_S
| I/F Depl |  |  |  |  | Business sanity check | . Make sure inventory adjustment data flow as expected for both VDC and KDC . Do an adjustment short to book and revert it by over to book reason code for VDC and KDC
#REF! | I/F Depl |  |  |  |  | Inform business about the progress on Inventory adjustment and upcoming impact on PO interface
#REF! | I/F Depl |  |  |  |  | $U Jobs Paused: PO and PO receipt interface between legacy purchasing and ebiz and wms | $U [UXAPP/LDBPRD/X] - WPO_MSGFLOW_S – (wom013/wom019 ¦ PO) - WMS_PO_RECEIPT_S | Sri | EC | Pending |  | NA
#REF! | I/F Depl |  |  |  |  | OSB deployment | - Deploy the WholesalePurchaseOrderListener - Deploy the WMSPOReceiptListener
#REF! | I/F Depl | 432557 |  |  | Y | Code check OSB deployment | . Make sure all OSB projects' codes are deployed successfully | Sri/Emily |  | Pending
#REF! | I/F Depl | 432557 | 1 |  |  | SOA deployment | Do the deployments below : - Deploy EbsReceiptSubscriberTecsys | Sri | DBA-Middleware | Pending | [5 empty] | Please refer to KDC interface release note for detailed steps: http://subversion.bcliquor.com/svn/SOA/ESB/tags/RLS_432557_WMS_Liquor_KDC_Release/Deploy/PROD-Release_Note_v1.0.0.txt
| I/F Depl |  |  |  |  | Code check for SOA deployment
#REF! | I/F Depl |  |  |  |  | Enable $U Jobs | $U [UXAPP/LDBPRD/X] - WPO_MSGFLOW_S – (wom013/wom019 ¦ PO) - WMS_PO_RECEIPT_S
| I/F Depl |  |  |  |  | Notify Business PO I/F deployment is done and start sanity check | . Make sure PO data flow as expected for both VDC and KDC DP to push an outstanding PO for KDC and VDC DC to receive PO for KDC and VDC
#REF! | I/F Depl |  |  |  |  | Inform business about the progress and the upcoming impact on SO
#REF! | I/F Depl |  |  | 6:30PM |  | $U Jobs Paused | $U [UXAPP/LDBPRD/X] - WMS_SHIP_CONFIRM_S - WMS_CANCEL_SALES_ORDER_S | Sri | EC | Pending |  | NA
#REF! | I/F Depl |  |  | 6:45PM |  | Retire and shutdown SOA composites | Retire the following SOA composites: - EBS partition/ EbsPickOrderPublisher [2.1] - (WOM16 ¦ Pick Order) | Sri | DBA-Middleware | Pending
#REF! | I/F Depl |  |  | 7:00PM | Y | Sanity check | Make sure $U jobs are disable and SOA composites are retired | Sri |  | Pending
#REF! | I/F Depl | 432557 | 1 |  |  | SOA deployment precheck | make sure there're no records in the pick order staging table re-push the messages if there's any? | Sri/Emily | Sri | Pending
#REF! | I/F Depl | 432557 | 1 |  |  | SOA deployment WOM16 - pick order from ebiz | Do the deployments below : - Deploy EbsPickOrderPublisher and disable | Sri | DBA-Middleware | Pending | [5 empty] | Please refer to KDC interface release note for detailed steps: http://subversion.bcliquor.com/svn/SOA/ESB/tags/RLS_432557_WMS_Liquor_KDC_Release/Deploy/PROD-Release_Note_v1.0.0.txt
#REF! | I/F Depl |  |  |  |  | Temporarily retire the newly deployed SOA composite | Retire the following SOA composites: - EBS partition/ EbsPickOrderPublisher [2.3] - (WOM16 ¦ Pick Order) | Sri |  | Pending
#REF! | I/F Depl |  |  |  | Y | Sanity check code deployment | Check if SOA composites deployed successfully | Sri/Emily |  | Pending
#REF! | I/F Depl |  |  |  |  | Enable $U Jobs | $U [UXAPP/LDBPRD/X] - WMS_SHIP_CONFIRM_S - WMS_CANCEL_SALES_ORDER_S
#REF! | I/F Depl |  |  |  |  | Activate SOA composite | Activate the following SOA composites: - EBS partition/ EbsPickOrderPublisher [2.3] - (WOM16 ¦ Pick Order) | Sri/Emily | DBA-Middleware | Pending
| I/F Depl |  |  |  |  | Notify Business SO I/F deployment is done and start sanity check
#REF! | I/F Depl | 432557 | 6 |  |  | Deploy Ebiz changes for DC 2 DC transfer | eBiz setup Inventory lookup code | Emily | Emily | Pending
#REF! | I/F Depl |  |  |  | Y | Sanity check on Ebiz deploymnet | Verify eBiz setup changes are deployed successfully | Emily |  | Pending
#REF! | I/F Depl | 432557 | 7 |  |  | remove DC2DC reason code | Login into WMS DB and run the delete script below against the WMS DB/Schema: DELETE FROM RS_F WHERE RSN_CODE IN ('70_WAREHOUSE_TRANSFER', '71_VDC_VDC_TRANSFER'); this should delete two records from each warehouse. | Sri/Emily | SQL-DBA/Sri | Pending
#REF! | I/F Depl |  |  |  | Y | Make sure item initial load is done | Before enabling Product messge flow | Sri |  | Pending
#REF! | I/F Depl |  |  |  |  | Schedule DC2DC task in Tecsys | Schedule task view LDB DC-to-DC Transfer (wms_up_ship.xf_ldb) to run every 5 minutes. Retry setting Save the schedule with Task Name = "dc-to-dc_transfer" | Sri | Angela | Pending
#REF! | I/F Depl |  |  |  | Y | Check the timer for DC2DC task is active | Tecsys Task view, look for action name = 'wms_xf_ldb' | Sri
#REF! | I/F Depl |  |  |  |  | Enable KDC users in Tecys WMS | Check out script to bulk disable all KDC only users from SVN http://subversion.bcliquor.com/svn/WMS/Liquor/02-PROJECTS/KDC Deployment/UserList . EnableKDCusers.sql
#REF! | I/F Depl |  |  |  |  | Sanity check DC2DC | 1. DP create ISO order from ebiz vdc to kdc, can be done ahead of time 2. After WOM15/16, manually release the order to wms VDC (Doug) 3. in VDC, DC to pick and ship complete 4. Validate ship complete is done in ebiz and intransit shipment(Emily) 5. in KDC, plan and create inbound PO XF receipt, receipt close out 6. validate the intransit receipt in ebiz (Emily)
#REF! | I/F Depl |  |  |  |  | Confirm interface sanity check completed by business |  | Doug
#REF! | I/F Depl |  |  |  |  | Communicate to business for enabling KDC users in Tecsys | Email to Glen Firman, Doug McDonald, John Sweet, Ken McDonnell, David Campbell, Hector Wong | James | NA
#REF! | I/F Depl |  |  |  |  | Enable KDC users in Tecys WMS | Check out script to bulk disable all KDC only users from SVN http://subversion.bcliquor.com/svn/WMS/Liquor/02-PROJECTS/KDC Deployment/UserList . EnableKDCusers.sql
#REF! | I/F Depl |  |  |  |  | Inform the business of the progress | Reuse the previous message | James | NA | Pending
#REF! | I/F Depl |  |  |  |  | Contingency if we go beyond the maintenance window | ??? |  |  | Pending
#REF! | Maintenance Window Ends AM
#REF! | I/F Depl |  |  |  |  | List of PO to be repush to tecsys KDC | compare the list with RB PO | Emily/Sri | DBA-oracle | Pending
#REF! | I/F Depl |  |  |  |  | List of SO to be repush to tecsys KDC | Script to extract for RB | Emily/Sri
#REF! | I/F Depl |  |  |  |  | Repush PO to tecsys KDC | RB PO + Queued PO | Sri/Emily/Andrei | DBA-Middleware | Pending
#REF! | I/F Depl |  |  |  |  | Verify POs land in tecsys KDC |  | Sri/Emily/Andrei
#REF! | I/F Depl |  |  |  |  | Repush SO to tecsys | RB SO + newly arrive SO | Sri/Emily/Andrei
#REF! | I/F Depl |  |  |  |  | Verify SOs land in tecsys KDC |  | Sri/Emily/Andrei
#REF! | <Date> - Business Verification
#REF!
#REF! |  |  |  |  | Y | Business verifications Sales order, PO, etc |  | Business | NA | Pending
#REF!
#REF! | Buying Guide |  |  |  | Y | Business verifies the BG (BI) and PAR |  | Demmand planners | NA | Pending |  | NA
#REF! | Monday Februray 29 - Business Go-Live
#REF! | Business Go-Live | NA | NA | [6 empty] | Pending
#REF! | Business Go-Live | NA | NA |  | Y | On-site verification of all features |  | James | NA | Pending
#REF! | Post deployment |  |  |  |  | Post deployment clean up | Delete the DB/application backup files | Sri/Emily/Andrei | SQL-DBA | Pending
[6 empty] | delete / retire old SOA component for WOM16, adjustoment, PO receipt |  | Sri
Orio check RB for connection disable, cehck with wendy Ops, RB every statuday/Sunday check by support center
RB every statuday/Sunday check by support center,

## KDC RLS
RLS | INT1 | INT3 | Jira |  |  | requirement
464278 |  | 464281 |  | KDC Warehouse Configuration | mitool | link
464278 | 521016 | 521013 |  | Container type | mitool
464278 | 527075 | 525748 |  | Mobile equipment | mitool
464278 |  |  |  | K tag | mitool
464278 |  | 50777 |  | carrier station configuration | SQL
464278 | 523213 | 500910 |  | wms system properties | SQL
464278 | 527951 |  | LWMS-128 | Pallet wrapper settings | SQL
492038 |  |  | LWMS-260 KDC-502 | KDC user to see DDC TiHi | mdtool
495193 | 499094 | 499089 | KDC-684 | DC-to-DC Transfer: iTopia Rule . Need to manually Schedule task view LDB DC-to-DC Transfer (wms_up_ship.xf_ldb) to run every 5 minutes. | mdtool | link
510489 |  |  | LWMS-111 | Warehouse search criteria | SQL, mdtool
432577 |  |  |  | NEW Item Master Requirements All interfaces including DC2DC transfer interface changes, etc. |  | link
432577 |  |  |  | Tunnel flip | mdtool
484626 |  |  | KDC-570 | Prompt to contact supervisor when getting replenishment and picks from certain Bulk Locations | mdtool | link
491878 |  |  | KDC-262 | When receiving product into DC, allow the Receiver to put product on HOLD | mdtool | link

## VDC RLS
RLS | Status | INT3 | INT1 | INT1 Status | Down Time
RLS-493114 | In Prod | Y | 521263 | Y |  | LWMS-135 | Item SCC label reprint ability (S010)
RLS-473871 | In Prod | Y | 518636 | Y |  | LWMS-32 | Inbound summary report changes (S019)
RLS-520868 | In Prod | Y | 521376 | Y |  | LWMS-116 | PO Unit of Measure Validation at PO Receiving
RLS-520930 | In Prod | Y | 520932 | Y |  | LWMS-108 | Inventory Adjustment 10_Resolved Bug
RLS-458280 | In Prod | Y | 466699 | Y |  | LWMS-82 | Bottle Pick Tower - UOM for picking Case Quantities in Bottle Pick Tower (S014)
RLS-525019 | In Prod | Y |  | Y |  | LWMS-245 | Deploy Tecsys patch EW-147629B_BCLDB_20191126082234 (Wave planning logging patch)
RLS-515299 | In Prod | Y |  | Y |  | LWMS-114 | Add Release Time column into LDB Pick by Order view
RLS-515299 | In Prod | Y |  | Y |  | LWMS-30 | LDB Loaders View add column for Last Transaction Date/Time
RLS-515299 | In Prod | Y |  | Y |  | LWMS-29 | Add column for - LDB Shipment Status
RLS-515299 | In Prod | Y |  | Y |  | LWMS-26 | Add field "Forward Pick Lot" to the LDB Locations - Full Access view (WMS_lc_f_full_ldb)
RLS-515299 | In Prod | Y |  | Y |  | LWMS-25 | Update shipment edit with addition fields
RLS-523565 | In Prod |  |  |  |  | LWMS-43 | Location-Based Inventory Aging Report
| In Prod |  |  |  |  | LWMS-41 | Operations Scorecard
| In Prod |  |  |  |  | LWMS-38 | Wave-related reports - Create LDB Forecasted Replenishment bottle version
| In Prod |  |  |  |  | LWMS-36 | Wave-related reports - update LDB Forecasted Replenishment
| In Prod |  |  |  |  | LWMS-34 | Inventory Control Audit
| In Prod |  |  |  |  | LWMS-33 | Wave-related reports - Countdown
| In Prod |  |  |  |  | LWMS-31 | Pre-Wave Audit Report
RLS-525463 | In Prod | [5 empty] | Updated the WMS Interface to use the new update views from TECSYS
RLS-523766 | In Prod | [5 empty] | Load balancer configuration and testing in INT5 for the scanner / desktop traffic - Changing GTM entry
RLS-522372 | ReadyForUAT | Y |  |  |  | LWMS-169 | Update iTopia Rules to set Product Break UOM's to UOM1 value | Pre-requisite to KDC: Data clean up for item break UOM before KDC item initial load
RLS-530701 | Ready for Production | Y |  | Y |  | LWMS-256 | When trying to create inventory in a pick location assigned to another item we get a non sensical message
529383 | ReadyForUAT | Y |  |  |  | LWMS-268 | LDB Inventory Relocation (RF) is missing UOM against current quantity which may lead to confusion on what is been adjusted
490113 | ReadyForProd | Y |  |  | 1-2h | LWMS-66 | Audit Database (S032) | add resource metaaudit_home_menu to role metaaudit_viewer
523413 | ReadyForUAT | Y |  |  | 10min | LWMS-42 | Need to identify and deprioritize non demand replenishment
RLS-486390 | ReadyForUAT | Y |  |  | 10min | LWMS-212 | Review most screens - case quantities to be displayed for everything but bottle tower (S040) | KEEP IT LAST ONE
RLS-476356 | ReadyForUAT | Y | 476700 |  |  | LWMS-110 | Pick Short Summary Report
521437, 512848 | ReadyForProd | 521433 |  |  |  | LWMS-224 | DB Job for WMS Interface Tables Archiving and Purging
RLS-544419 | Dev in Progress |  |  |  |  | LWMS-416 | BOL incorrect in TecSys causing potential cost to LDB | If this one in production before KDC, remove the sql from http://subversion.bcliquor.com/svn/WMS/Liquor/02-PROJECTS/KDC Deployment/30-SQL