## Sheet1
Billing Month
2021-04-09
Week Ending (Saturday)
2021-04-10
Contractor Name |  |  |  |  | Company
BIKRAMJIT S KAHLON |  |  |  |  | ANNEX CONSULTING GROUP
Project Name: |  |  |  |  | Wholesale Operations = 32 Hours
Day | Date | Hours | Description of Work Completed | [5 empty] | Hours
Sun | 2021-04-04 | 0
Mon | 2021-04-05 | 0
STAT HOLIDAY - EASTER
Tue | 2021-04-06 | 8
WMS Utils
|  |  | -- Development of Stuck in TRUCK - 3rd senario | [5 empty] | 4
WMS Support - KT
|  |  | -- Tecsys 201 KT session for Team | [5 empty] | 2
|  |  | -- Webstore setup on local | [5 empty] | 2
Wed | 2021-04-07 | 8
WMS Utils
|  |  | -- Cont. development of Stuck in TRUCK - 3rd senario | [5 empty] | 5
WMS Support
|  |  | --Webstore development enviorment setup | [5 empty] | 3
Thu | 2021-04-08 | 8
WMS Support - KT
|  |  | -- KT preparation and enviorment setup | [5 empty] | 3
|  |  | --Tecsys 201 KT Session 4 with team | [5 empty] | 2
|  |  | --Webstore development enviorment setup | [5 empty] | 3
Fri | 2021-04-09 | 8
WMS Support
|  |  | -- Developed new Tecsys view for Replenishment Wave messahe fix | [5 empty] | 5
|  |  | -- Unit testing and Task Review | [5 empty] | 1
|  |  | --deployment preparation and INT5 release | [5 empty] | 2
Sat | 2021-04-10 | 0
| Total Hours | 32
| Contractor Signature |  |  | Direct Report Initials |  | PM Signature |  | LDB Signature
Bikramjit Singh Kahlon
Formulas:
Date = [Date, row below]-1
Contractor’s Weekly Timesheet