## Sheet1
Billing Month
2017-11-10
Week Ending (Saturday)
2017-11-11
Contractor Name |  |  |  | Company
BIKRAMJIT S KAHLON |  |  |  | ANNEX CONSULTING GROUP
Project Name: |  |  |  | WMS Project = 40 Hours
Day | Date | Hours | Description of Work Completed |  |  |  | Hours
Sun | 2017-11-05 | 0
Mon | 2017-11-06 | 8 | Scrum Meeting |  |  |  | 0.5
|  |  | Mi-Tool - code refactoring |  |  |  | 7.5
Tue | 2017-11-07 | 8 | Scrum Meeting |  |  |  | 0.5
|  |  | Mi-Tool - developed command line utility for Import and Export |  |  |  | 7.5
Wed | 2017-11-08 | 8 | WMS project Meeting |  |  |  | 1.5
|  |  | Mi-Tool - development create user restrition and warehouse access |  |  |  | 5
|  |  | Mi-Tool - testing user-restriction and user warehouse access |  |  |  | 1.5
Thu | 2017-11-09 | 8 | Scrum Meeting |  |  |  | 0.5
|  |  | Mi-Tool - Code refactoring and testing |  |  |  | 7.5
Fri | 2017-11-10 | 8 | Scrum Meeting |  |  |  | 0.5
|  |  | Mi-Tool - Code clean up and testing |  |  |  | 5.5
|  |  | Mi-Tool - trouble-shooting missing location class |  |  |  | 1
|  |  | Mi-Tool - demo to wms team |  |  |  | 1
Sat | 2017-11-11 | 0
| Total Hours | 40
| Contractor Signature |  |  | PM Signature |  | LDB Signature
Raymundo Villafuerte
Formulas:
Date = [Date, row below]-1
Contractor’s Weekly Timesheet