## Sheet1
Billing Month
2020-07-17
Week Ending (Saturday)
2020-07-18
Contractor Name |  |  |  |  | Company
BIKRAMJIT S KAHLON |  |  |  |  | ANNEX CONSULTING GROUP
Project Name: |  |  |  |  | Hospitality Pricing = 58 Hours
Day | Date | Hours | Description of Work Completed | [5 empty] | Hours
Sun | 2020-07-12 | 0
Mon | 2020-07-13 | 9
Hospitality Pricing
|  |  | -- Pricing file deployment and testing in INT5 | [5 empty] | 2
|  |  | -- Review data conversion scripts and evaluated the risk | [5 empty] | 3
|  |  | -- Deployment Planning and scheduling | [5 empty] | 2
|  |  | -- Team review and co-ordination | [5 empty] | 2
Tue | 2020-07-14 | 12
Hospitality Pricing
|  |  | -- Project Deployment planning and sequncing | [5 empty] | 3
|  |  | -- Identify denpencies and risk evaluations | [5 empty] | 2
|  |  | -- Team meetings | [5 empty] | 3
|  |  | WMS - Defect fixes Receipt Close-out due to archiving | [5 empty] | 4
Wed | 2020-07-15 | 11
Hospitality Pricing
|  |  | -- Webstore impact analysis review and planning | [5 empty] | 3
|  |  | -- Team Meetings - Standup, review and planning | [5 empty] | 4
|  |  | --Retail Store deployment planning review | [5 empty] | 2
|  |  | -- Defect review and fixes | [5 empty] | 2
Thu | 2020-07-16 | 11
Hospitality Pricing
|  |  | --Datawarehousing deployment review and planing | [5 empty] | 3
|  |  | --Team meetings - Status updates and review | [5 empty] | 5
|  |  | -- SPI application deployment preparation and planing | [5 empty] | 3
Fri | 2020-07-17 | 11
Hospitality Pricing
|  |  | -- Review Data conversion and INT5 SIT deployments | [5 empty] | 1
|  |  | -- HPI application changes and deployments review | [5 empty] | 4
|  |  | -- Retail Store/OES application deployment review and planning | [5 empty] | 3
|  |  | -- Defect triage and solutioning | [5 empty] | 3
Sat | 2020-07-18 | 4 | HP - Retail Store deployment, Planing next release and execution | [5 empty] | 4
| Total Hours | 58
| Contractor Signature |  |  | Direct Report Initials |  | PM Signature |  | LDB Signature
Bikramjit Singh Kahlon
Formulas:
Date = [Date, row below]-1
Contractor’s Weekly Timesheet