## Sheet1
Billing Month
2020-08-07
Week Ending (Saturday)
2020-08-08
Contractor Name |  |  |  |  | Company
BIKRAMJIT S KAHLON |  |  |  |  | ANNEX CONSULTING GROUP
Project Name: |  |  |  |  | Hospitality Pricing = 54 Hours
Day | Date | Hours | Description of Work Completed | [5 empty] | Hours
Sun | 2020-08-02 | 9 | WS PriceService - getPrices Performance Improvement dev. | [5 empty] | 9
Mon | 2020-08-03 | 11
Hospitality Pricing
|  |  | -- WS Price Service - Perfomance Improvement development | [5 empty] | 6
|  |  | -- WS Price Service - Unit testing | [5 empty] | 3
|  |  | -- WS Price Service Integartion testing | [5 empty] | 2
Tue | 2020-08-04 | 9
Hospitality Pricing
|  |  | -- Vendor Service - Performance improvemement fixes to HPI application | [5 empty] | 6
|  |  | -- Performed Unit Testing for Vendor service fix | [5 empty] | 3
Wed | 2020-08-05 | 10
Hospitality Pricing
|  |  | -- Blacklist SKU development fixes and change review | [5 empty] | 6
|  |  | -- Business review for the UI layout changes and fixes | [5 empty] | 4
Thu | 2020-08-06 | 9
Hospitality Pricing
|  |  | -- Blacklist SKU development and Fixes | [5 empty] | 5
|  |  | -- Layout changes and fixes | [5 empty] | 4
Fri | 2020-08-07 | 6
Hospitality Pricing
|  |  | -- Review Pricing Calender layout changes | [5 empty] | 2
|  |  | -- Deploy Blacklisted SKU changes in Development enviorment and Testing | [5 empty] | 4
Sat | 2020-08-08 | 0
| Total Hours | 54
| Contractor Signature |  |  | Direct Report Initials |  | PM Signature |  | LDB Signature
Bikramjit Singh Kahlon
Formulas:
Date = [Date, row below]-1
Contractor’s Weekly Timesheet