## Sheet1
Billing Month
2020-08-28
Week Ending (Saturday)
2020-08-29
Contractor Name |  |  |  |  | Company
BIKRAMJIT S KAHLON |  |  |  |  | ANNEX CONSULTING GROUP
Project Name: |  |  |  |  | Hospitality Pricing = 59 Hours
Day | Date | Hours | Description of Work Completed | [5 empty] | Hours
Sun | 2020-08-23 | 10 | LDB Item getHospitalityProducts api development | [5 empty] | 10
Mon | 2020-08-24 | 9
Hospitality Pricing
|  |  | -- LDB Item service build and deployment in development enviorment | [5 empty] | 2
|  |  | --getHospitalityProducts api unit testing and fixes | [5 empty] | 4
|  |  | -- HPI application blacklisted SKU fixes and review | [5 empty] | 3
Tue | 2020-08-25 | 10
Hospitality Pricing
|  |  | -- LDB Item service INT5 deployment and prepare for SIT | [5 empty] | 3
|  |  | -- Support SIT and service validation and performance testing | [5 empty] | 4
|  |  | -- Project Team meeting and HPI application performance review | [5 empty] | 2
|  |  | -- Review SOA service build and testing | [5 empty] | 1
Wed | 2020-08-26 | 11
Hospitality Pricing
|  |  | -- LDB Item Contract changes to fix the Gap | [5 empty] | 3
|  |  | -- getHospitalityProducts fix for Container elements | [5 empty] | 4
|  |  | -- Unit Testing and deployment to Development | [5 empty] | 2
|  |  | -- Deployment Plan prepartion | [5 empty] | 2
Thu | 2020-08-27 | 9
Hospitality Pricing
|  |  | -- getHospitalityProducts contaier fixes deployment to INT5 | [5 empty] | 2
|  |  | -- HPI application service integartion with new API | [5 empty] | 4
|  |  | -- Project deployment Plan prepartion for pre-golive and team meetings | [5 empty] | 3
Fri | 2020-08-28 | 10
Hospitality Pricing
|  |  | -- Production deployment and verification of Wholesale Price repository | [5 empty] | 4
|  |  | -- Production deployment prepartion for Sunday | [5 empty] | 3
|  |  | --Load testing of HPI application | [5 empty] | 3
Sat | 2020-08-29 | 0
| Total Hours | 59
| Contractor Signature |  |  | Direct Report Initials |  | PM Signature |  | LDB Signature
Bikramjit Singh Kahlon
Formulas:
Date = [Date, row below]-1
Contractor’s Weekly Timesheet